## Trajectory
Status | Site Address | Ward new | Ward old | Source Reference | LOCAL PLAN DESIGNATION | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | Remaining supply | PLAN PERIOD TOTAL
BROAD LOCATION | Brent Cross West (Staples Corner) Growth Area | Cricklewood | Golders Green | Policy GSS03 | BRENT CROSS WEST (STAPLES CORNER) GROWTH AREA | 2032-33: 450; 2033-34: 450; 2034-35: 450; 2035-36: 450 | 1800 | 1800
BROAD LOCATION | New Southgate Opportunity Area | Friern Barnet | Coppetts | Policy GSS09 | PUBLIC TRANSPORT INFRASTRUCTURE | 2031-32: 50; 2032-33: 50; 2033-34: 50; 2034-35: 50; 2035-36: 50 | 250 | 250
UNDER CONSTRUCTION | Basing Way Green | Garden Suburb | Finchley Church End | Barnet Homes 19/6610/FUL | OTHER SITES | 2022-23: 46 | 46 | 46
CONSENT | Crown Honda, Hyde Estate Road, NW9 6JX | West Hendon | Colindale | 20/3906/FUL | MAJOR THOROUGHFARE | 2026-27: 166; 2028-29: 304 | 470 | 470
PROPOSED ALLOCATION | 309-319 Ballard's Lane North Finchley N12 8LY | West Finchley | West Finchley | North Finchley SPD | NORTH FINCHLEY TOWN CENTRE | 2029-30: 42; 2030-31: 41 | 83 | 83
UNDER CONSTRUCTION | Premier Place, 102-124 Station Road And Car Park To Rear, HA8 7BJ | Edgware | Edgware | 16/0112/FUL | EDGWARE GROWTH AREA | 2023-24: 122 | 122 | 122
CONSENT | Land at the Rectory, Rectory Lane, HA8 7LG | Edgware | Edgware | 18/2839/FUL | EDGWARE GROWTH AREA | 2024-25: 51 | 51 | 51
PROPOSED ALLOCATION | 45-69 East Barnet Rd, EN4 8RN | East Barnet | East Barnet | New Barnet Town Centre Strategy | NEW BARNET TOWN CENTRE | 2028-29: 38; 2029-30: 37 | 75 | 75
UNDER CONSTRUCTION | Land At Broadfields Primary School Roseberry Drive, Edgware, HA8 8JP | Edgware | Edgware | 20/4031/FUL | OTHER SITES | 2023-24: 137 | 137 | 137
CONSENT | 65 Watford Way, NW4 3AQ | West Hendon | West Hendon | 20/1898/PNO | HENDON CENTRAL TOWN CENTRE | 2023-24: 19 | 19 | 19
CONSENT | Broadfields Estate Bushfield Crescent Edgware HA8 8XH | Edgwarebury | Edgware | 20/3742/FUL | OTHER SITES | 2026-27: 28 | 28 | 28
UNDER CONSTRUCTION | 100 Burnt Oak Broadway, Edgware, HA8 0BE | Burnt Oak | Burnt Oak | 19/1049/FUL | BURNT OAK TOWN CENTRE | 2023-24: 100 | 100 | 100
COMPLETED | 92, Hillview Gardens, NW4 2JR | Hendon | Hendon | 19/0960/FUL | OTHER SITES | 2021-22: 40 | 0 | 40
COMPLETED | Former Hendon Hall Hotel, 28 Ashley Lane, NW4 1HF | Hendon | Hendon | 18/3068/FUL | OTHER SITES | 2021-22: 102 | 0 | 102
COMPLETED | Stag House | Burnt Oak | Burnt Oak | Barnet Homes 17/8140/FUL | BURNT OAK TOWN CENTRE | 2021-22: 51 | 0 | 51
CONSENT | Colesworth House, Crokesley House, Curtlington House, Clare House and Kedyngton House, Burnt Oak Broadway, HA8 | Burnt Oak | Burnt Oak | 19/2657/FUL Barnet Homes | BURNT OAK TOWN CENTRE | 2025-26: 18 | 18 | 18
COMPLETED | 186 High Street, Edgware, HA8 7EX | Edgwarebury | Edgware | 18/4685/FUL | OTHER SITES | 2021-22: 20 | 0 | 20
UNDER CONSTRUCTION | Imperial House, the Hyde, NW9 5AL | Colindale South | Colindale | APP/N5090/W/16/3158645 15/04442/FUL 19/2897/FUL | COLINDALE GROWTH AREA | 2023-24: 102 | 102 | 102
ALLOCATION -AAP | Merit House, Edgware Road, NW9 5AB | West Hendon | Colindale | Colindale AAP | COLINDALE GROWTH AREA | 2029-30: 85; 2030-31: 95 | 180 | 180
PROPOSED ALLOCATION | 744-776 High Rd North Finchley N12 9QG/9QS | West Finchley | Woodhouse | North Finchley SPD | NORTH FINCHLEY TOWN CENTRE | 2030-31: 112 | 112 | 112
ALLOCATION -AAP | Kwik Fit - The Hyde (adj Kidstop) | Colindale North | Colindale | Colindale AAP | COLINDALE GROWTH AREA | 2029-30: 30; 2030-31: 30 | 60 | 60
OTHER | Land Adjacent Northway And Fairway Primary School The Fairway Mill Hill London NW7 3HS | Edgware | Hale | Council Assets Disposal Programme 15/03138/FUL | OTHER SITES | 2025-26: 60; 2026-27: 60 | 120 | 120
PROPOSED ALLOCATION | 811 High Rd North Finchley & Lodge Lane carpark N12 8JT | West Finchley | West Finchley | North Finchley SPD | NORTH FINCHLEY TOWN CENTRE | 2027-28: 66; 2028-29: 66 | 132 | 132
PROPOSED ALLOCATION | Allum Way Totteridge & Whetstone station/High Rd/Download Close/Allum Way N20 | Totteridge & Woodside | Totteridge | Call for sites | WHETSTONE TOWN CENTRE | 2027-28: 150; 2028-29: 150; 2029-30: 150; 2030-31: 149 | 599 | 599
PROPOSED ALLOCATION | Army Reserve Depot | High Barnet | High Barnet | Chipping Barnet town centre strategy | CHIPPING BARNET TOWN CENTRE | 2034-35: 100; 2035-36: 93 | 193 | 193
OTHER | Colindale Station Colindale Avenue NW9 5HR | Colindale South | Colindale | 19/0859/OUT Colindale Station SPD | COLINDALE GROWTH AREA | 2027-28: 100; 2028-29: 113; 2029-30: 100 | 313 | 313
UNDER CONSTRUCTION | Douglas Bader Park Estate, Clayton Field, NW9 5SE | Colindale South | Colindale | 20/6277/FUL | ESTATES | 2024-25: -2; 2027-28: 286; 2031-32: 198 | 482 | 482
UNDER CONSTRUCTION | Grahame Park - Stage B | Colindale South | Colindale | 19/5493/OUT | ESTATES |  |  | 209 | -35 | -35 | 115 | 179 | 212 | 213 | 106 | 166 | 219 | 170 | 136 | 169 | 124 | 1948 | 1824
UNDER CONSTRUCTION | Colindale Telephone Exchange The Hyde, NW9 6LB | Colindale South | Colindale | 17/5534/PNO 18/0352/FUL | MAJOR THOROUGHFARE | 2026-27: 244; 2030-31: 261 | 505 | 505
PROPOSED ALLOCATION | B&Q, Broadway Retail Park, NW2 1ES | Cricklewood | Childs Hill | 20/3564/OUT | CRICKLEWOOD GROWTH AREA | 2026-27: 200; 2027-28: 200; 2028-29: 300; 2029-30: 300; 2030-31: 49 | 1049 | 1049
UNDER CONSTRUCTION | Sainsburys The Hyde NW9 6JX | Colindale South | Colindale | Call for sites 19/4661/FUL | MAJOR THOROUGHFARE | 2024-25: 200; 2025-26: 200; 2026-27: 300; 2027-28: 300; 2028-29: 309 | 1309 | 1309
COMPLETED | Colindale Gardens, Phase 2 (Blocks EFG), Aerodrome Road | Colindale South | Colindale | H/04753/14, 16/7836/S73, 19/0636/RMA | COLINDALE GROWTH AREA | 2021-22: 318 | 0 | 318
COMPLETED | Colindale Gardens, Phase 2 (Blocks ABCD), Aerodrome Road | Colindale South | Colindale | H/04753/14, 16/7836/S73, 19/2284/RMA | COLINDALE GROWTH AREA | 2021-22: 98 | 0 | 98
UNDER CONSTRUCTION | Colindale Gardens (Remainder of Stage 2) and Stage 3 | Colindale South | Colindale | H/04753/14, 16/7836/S73, 19,2284/RMA 19/6512/OUT | COLINDALE GROWTH AREA | 2022-23: 347; 2023-24: 373; 2024-25: 374; 2025-26: 212; 2026-27: 378; 2027-28: 258; 2028-29: 258; 2029-30: 259 | 2459 | 2459
PROPOSED ALLOCATION | Bingo Hall Cricklewood | Cricklewood | Childs Hill | Call for sites | CRICKLEWOOD GROWTH AREA | 2028-29: 38; 2029-30: 39 | 77 | 77
UNDER CONSTRUCTION | West Hendon Estate | West Hendon | West Hendon | H/01054/13 | ESTATES | 2022-23: 22; 2023-24: 223; 2024-25: 161; 2025-26: 115; 2026-27: 116; 2027-28: 394 | 1031 | 1031
PROPOSED ALLOCATION | Bobath Centre 250 East End Rd N2 8AU | East Finchley | East Finchley | 21/2602/FUL | EAST FINCHLEY TOWN CENTRE | 2026-27: 25 | 25 | 25
PROPOSED ALLOCATION | Brentmead Place 1-6 Brentmead Place NW11 9JG | Golders Green | Golders Green | Call for sites | MAJOR THOROUGHFARE | 2025-26: 46 | 46 | 46
UNDER CONSTRUCTION | Beaufort Park REMAINING Phases (Blocks D1-D7) | Burnt Oak | Colindale | H/02713/09, 20/0276/FUL, 14/07066/RMA | COLINDALE GROWTH AREA | 2024-25: 190; 2025-26: 295 | 485 | 485
COMPLETED | Beaufort Park REMAINING Phases (Blocks F1, F2, F8, F9) | Colindale South | Colindale | H/04672/14 | COLINDALE GROWTH AREA | 2021-22: 383 | 0 | 383
CONSENT | 107 West Hendon Broadway | West Hendon | West Hendon | 21/0932/FUL | MAJOR THOROUGHFARE | 2025-26: 37 | 37 | 37
CONSENT | 60 West Hendon Broadway | West Hendon | West Hendon | 17/6434/FUL | MAJOR THOROUGHFARE | 2024-25: 53 | 53 | 53
CONSENT | Brent Cottage, Brent Park Road, NW9 7AP | West Hendon | West Hendon | 21/2485/FUL | OTHER SITES | 2024-25: 63 | 63 | 63
PROPOSED ALLOCATION | Bunns Lane Carpark Bunns Lane NW7 2AA | Edgwarebury | Hale | Council Assets Disposal Programme | MILL HILL TOWN CENTRE | 2028-29: 43 | 43 | 43
PROPOSED ALLOCATION | Burroughs Gardens Carpark The Burroughs NW4 4AU | Hendon | Hendon | Council Assets Disposal Programme | HENDON CENTRAL TOWN CENTRE | 2027-28: 9 | 9 | 9
PROPOSED ALLOCATION | Central House and 1-9 Ballards Lane | West Finchley | West Finchley | Finchley Church End town centre strategy | FINCHLEY CENTRAL TOWN CENTRE | 2027-28: 42 | 42 | 42
PROPOSED ALLOCATION | East Barnet Library, EN4 8SG | East Barnet | East Barnet | Council Assets Disposal Programme | OTHER SITES | 2028-29: 12 | 12 | 12
ALLOCATION -AAP | Middlesex University Halls | West Hendon | Colindale | Colindale AAP | COLINDALE GROWTH AREA | 2029-30: 90; 2030-31: 100 | 190 | 190
PROPOSED ALLOCATION | East Barnet Shooting Club Victoria Rd EN4 9SH | East Barnet | East Barnet | Council Assets Disposal Programme | NEW BARNET TOWN CENTRE | 2032-33: 43 | 43 | 43
CONSENT | 46 Watford Way NW4 3AL | Hendon | Hendon | 20/1111/FUL | HENDON CENTRAL TOWN CENTRE | 2025-26: 60 | 60 | 60
PROPOSED ALLOCATION | East Finchley Station Carpark N2 0NW | East Finchley | East Finchley | Call for sites | EAST FINCHLEY TOWN CENTRE | 2031-32: 70; 2032-33: 65 | 135 | 135
PROPOSED ALLOCATION | East Finchley Substation N2 0NL | East Finchley | East Finchley | Call for sites | EAST FINCHLEY TOWN CENTRE | 2026-27: 9 | 9 | 9
PROPOSED ALLOCATION | East Wing, 672-708 High Rd North Finchley N12 9PT/9QL | Woodhouse | Woodhouse | North Finchley SPD | NORTH FINCHLEY TOWN CENTRE | 2029-30: 40; 2030-31: 40 | 80 | 80
PROPOSED ALLOCATION | Edgware Hospital | Burnt Oak | Burnt Oak | Call for sites | MAJOR THOROUGHFARE | 2028-29: 129 | 129 | 129
UNDER CONSTRUCTION | Fosters Estate, NW4 2DL | Hendon | Hendon | 19/2517/FUL | ESTATES | 2023-24: 47; 2024-25: 142 | 189 | 189
UNDER CONSTRUCTION | National Institute of Medical Research | Mill Hill | Mill Hill | 16/4545/FUL | MILL HILL EAST AREA | 2022-23: 85; 2023-24: 100; 2024-25: 105 | 290 | 290
CONSENT | 60 Station Road, EN5 1QG | Mill Hill | High Barnet | 20/4847/FUL | OTHER SITES | 2025-26: 12 | 12 | 12
CONSENT | Brent Cross Cricklewood - Brent Cross North | Cricklewood | Golders Green | F/04687/13 | BRENT CROSS GROWTH AREA | 2032-33: 200; 2033-34: 200; 2034-35: 200; 2035-36: 200 | 800 | 800
UNDER CONSTRUCTION | Brent Cross Cricklewood - Brent Cross Town | Cricklewood | Golders Green | F/04687/13, 17/6662/RMA, 18/6409/RMA, 18/6337/RMA, 20/5690/RMA, 21/0070/RMA, 21/4063/RMA, 22/5238/RMA | BRENT CROSS GROWTH AREA |  |  |  | 536 | 560 | 351 | 667 | 778 | 568 | 112 | 1023 | 363 | 109 | 452 | 324 | 62 | 5905 | 5843
UNDER CONSTRUCTION | Brent Cross Cricklewood - Brent Cross Town - Plots 25, 28 and 56- Student Housing | Cricklewood | Golders Green | F/04687/13 | BRENT CROSS GROWTH AREA | 2024-25: 240; 2029-30: 307; 2030-31: 240 | 787 | 787
PROPOSED ALLOCATION | Edgware Town Centre | Edgware | Edgware | Edgware Growth Area SPD | EDGWARE GROWTH AREA | 2029-30: 451; 2030-31: 451; 2031-32: 451; 2032-33: 452; 2033-34: 452 | 2257 | 2257
UNDER CONSTRUCTION | Westhorpe Gardens and Mills Grove NW4 2TU | Hendon | Hendon | 18/7495/FUL | ESTATES | 2023-24: 149 | 149 | 149
PROPOSED ALLOCATION | Edgware Underground & Bus Stations, HA8 7AW | Edgware | Edgware | Edgware Growth Area SPD | EDGWARE GROWTH AREA | 2027-28: 463; 2028-29: 463; 2029-30: 463; 2030-31: 462; 2031-32: 465 | 2316 | 2316
PROPOSED ALLOCATION | Egerton Gardens Carpark The Burroughs NW4 8BD | Hendon | Hendon | Call for sites | HENDON CENTRAL TOWN CENTRE | 2027-28: 25 | 25 | 25
PROPOSED ALLOCATION | Fayer's Building Yard & Church EN4 9NR | East Barnet | East Barnet | New Barnet Town Centre Strategy | NEW BARNET TOWN CENTRE | 2027-28: 25 | 25 | 25
SITE CLEARED | 194 - 196 Cricklewood Broadway, NW2 3EB | Cricklewood | Childs Hill | 17/0233/FUL | CRICKLEWOOD GROWTH AREA | 2025-26: 96 | 96 | 96
UNDER CONSTRUCTION | Mill Hill East (Millbrook Park) Phase 6b | Mill Hill | Mill Hill | Mill Hill AAP 15/06417/OUT 19/5827/FUL | MILL HILL EAST AREA | 2024-25: 50; 2025-26: 50; 2026-27: 36 | 136 | 136
PROPOSED ALLOCATION | Fenella The Burroughs NW4 4BS | Hendon | Hendon | Call for sites | BRENT STREET TOWN CENTRE | 2027-28: 65 | 65 | 65
CONSENT | Yamor House 285 Golders Green Road London NW11 9JE | Golders Green | Golders Green | 21/4742/FUL | OTHER SITES | 2026-27: 22 | 22 | 22
PROPOSED ALLOCATION | Finchley Central Station N3 2RY | Finchley Church End | Finchley Church End | Call for sites | FINCHLEY CENTRAL TOWN CENTRE | 2027-28: 14; 2028-29: 135; 2029-30: 136; 2030-31: 135; 2031-32: 136 | 556 | 556
COMPLETED | Mill Hill East (Millbrook Park) Phase 6 | Mill Hill | Mill Hill | Mill Hill AAP H/03904/12 18/6352/RMA | MILL HILL EAST AREA | 2021-22: 310 | 0 | 310
COMPLETED | Mill Hill East (Millbrook Park) Phase 4b | Mill Hill | Mill Hill | Mill Hill AAP H/03904/12 16/3111/RMA | MILL HILL EAST AREA | 2021-22: 188 | 0 | 188
COMPLETED | Mill Hill East (Millbrook Park) Phase 5 | Mill Hill | Mill Hill | Mill Hill AAP H/03904/12 17/3304/RMA | MILL HILL EAST AREA | 2021-22: 149 | 0 | 149
COMPLETED | Mill Hill East (Millbrook Park) Phase 4c | Mill Hill | Mill Hill | Mill Hill AAP H/03904/12 18/0635/RMA | MILL HILL EAST AREA | 2021-22: 87 | 0 | 87
CONSENT | Mill Hill East (Millbrook Park) Phases 7 and 8 | Totteridge & Woodside | Mill Hill | Mill Hill AAP H/03904/12 19/3092/RMA | MILL HILL EAST AREA | 2023-24: 90; 2024-25: 80; 2025-26: 80; 2026-27: 80 | 330 | 330
UNDER CONSTRUCTION | 1-5 Princes Parade, Golders Green Road and 1-3 Heather Gardens NW11 9HS | Golders Green | Garden Suburb | 18/2492/FUL 19/4784/FUL | OTHER SITES | 2022-23: 22 | 22 | 22
CONSENT | Coniston Court, 5 Langstone Way, NW7 1GP (Supported Living) | Totteridge & Woodside | Mill Hill | 21/2290/FUL | MILL HILL EAST AREA | 2024-25: 30 | 30 | 30
CONSENT | 290-294 Golders Green Road, NW11 9PY | Golders Green | Garden Suburb | 16/3806/FUL 19/6857/FUL | OTHER SITES | 2024-25: 111 | 111 | 111
COMPLETED | Mill Hill East (Millbrook Park) Phase 10 | Mill Hill | Mill Hill | Mill Hill AAP 18/2891/RMA | MILL HILL EAST AREA | 2021-22: 110 | 0 | 110
UNDER CONSTRUCTION | Mill Hill East (Millbrook Park) Phase 9 | Totteridge & Woodside | Mill Hill | Mill Hill AAP H/03904/12 19/3092/RMA | MILL HILL EAST AREA | 2022-23: 155 | 155 | 155
UNDER CONSTRUCTION | 141-143 Dollis Road NW7 1JX | Mill Hill | Mill Hill | 17/3796/FUL | OTHER SITES | 2022-23: 23 | 23 | 23
PROPOSED ALLOCATION | Finchley House, High Rd & Kingsway North Finchley N12 0BT | West Finchley | West Finchley | North Finchley SPD | NORTH FINCHLEY TOWN CENTRE | 2027-28: 64; 2028-29: 64 | 128 | 128
COMPLETED | Brake Shear House 164 High Street Barnet EN5 5XP | High Barnet | High Barnet | 16/2466/FUL 18/4700/FUL | CHIPPING BARNET TOWN CENTRE | 2022-23: 58 | 58 | 58
UNDER CONSTRUCTION | Granville Road | Childs Hill | Childs Hill | APP/N5090/W/15/3132049 F/04474/14 | ESTATES | 2023-24: 33; 2024-25: 99 | 132 | 132
PROPOSED ALLOCATION | Former Barnet Mortuary, N3 2EU | Woodhouse | Woodhouse | 22/3385/FUL | MAJOR THOROUGHFARE | 2025-26: 60 | 60 | 60
UNDER CONSTRUCTION | Dollis Valley - Phase 3 | High Barnet | Underhill | B/00354/13 | ESTATES | 2022-23: 137 | 137 | 137
CONSENT | Dollis Valley - Phases 4 and 5 | Underhill | Underhill | B/00354/13, 21/2407/RMA | ESTATES | 2024-25: -83; 2025-26: -83; 2026-27: 55; 2027-28: 55; 2028-29: 55; 2029-30: 58 | 57 | 57
UNDER CONSTRUCTION | Tower Service Station 617 Finchley Road London NW3 7BS | Childs Hill | Childs Hill | 16/5296/FUL | MAJOR THOROUGHFARE | 2023-24: 28 | 28 | 28
COMPLETED | Hermitage Lane | Cricklewood | Childs Hill | Barnet Homes 18/4674/FUL | OTHER SITES | 2022-23: 52 | 52 | 52
PROPOSED ALLOCATION | Former Church Farm Leisure Centre, EN4 8XE | East Barnet | Brunswick Park | Council Assets Disposal Programme | OTHER SITES | 2028-29: 12 | 12 | 12
PROPOSED ALLOCATION | Great North Leisure Park N12 0GL | Woodhouse | Woodhouse | Call for sites | MAJOR THOROUGHFARE | 2029-30: 176; 2030-31: 176 | 352 | 352
PROPOSED ALLOCATION | Great North Road Local Centre EN5 1AB | Barnet Vale | Oakleigh | Call for sites | MAJOR THOROUGHFARE | 2030-31: 27 | 27 | 27
COMPLETED | Finchley Police Station, 193, Ballards Lane | West Finchley | West Finchley | 19/2079/FUL | FINCHLEY CENTRAL TOWN CENTRE | 2021-22: 41 | 0 | 41
CONSENT | 38 - 44 Ballards Lane London N3 2BJ | West Finchley | West Finchley | 21/4977/FUL | FINCHLEY CENTRAL TOWN CENTRE | 2026-27: 22 | 22 | 22
PROPOSED ALLOCATION | High Barnet Station Carpark Great North Road EN5 5RP | High Barnet | High Barnet | 16/2466/FUL 18/4700/FUL | CHIPPING BARNET TOWN CENTRE | 2027-28: 92; 2028-29: 100; 2029-30: 100 | 292 | 292
PROPOSED ALLOCATION | Woodside Park Station West N12 8RT | Whetstone | Totteridge | Call for sites 19/4293/FUL (southern part of site 56) | PUBLIC TRANSPORT INFRASTRUCTURE | 2023-24: 86 | 86 | 86
PROPOSED ALLOCATION | IBSA House The Ridgeway NW7 1RN | Mill Hill | Mill Hill | Call for Sites 19/6551/FUL | MILL HILL EAST AREA | 2026-27: 197 | 197 | 197
SITE CLEARED | 66 Woodside Park Road, N12 8RY | Whetstone | Totteridge | 19/6833/FUL | OTHER SITES | 2024-25: 13 | 13 | 13
COMPLETED | Carmelite Friars, 63 East End Road, N2 0SE | East Finchley | East Finchley | 18/4221/FUL | OTHER SITES | 2022-23: 15 | 15 | 15
PROPOSED ALLOCATION | KFC/ Burger King, NW9 5EB | Colindale South | Colindale | Colindale AAP | COLINDALE GROWTH AREA | 2029-30: 51; 2030-31: 51 | 102 | 102
CONSENT | Rowlandson House, 289-293 Ballards Lane, N12 8NP | West Finchley | West Finchley | 19/0948/PNO | NORTH FINCHLEY TOWN CENTRE | 2022-23: 37 | 37 | 37
PROPOSED ALLOCATION | Land at Whalebones EN5 4BZ | Barnet Vale | High Barnet | Call for sites | OTHER SITES | 2027-28: 100 | 100 | 100
PROPOSED ALLOCATION | Mcdonalds Site, 157 Colindeep Lane, NW9 6BD | Colindale North | Colindale | Colindale AAP | COLINDALE GROWTH AREA | 2028-29: 56; 2029-30: 56 | 112 | 112
COMPLETED | Kingmaker House, 15 Station Road, Barnet, Herts, EN5 1NZ | Barnet Vale | Oakleigh | 16/0517/PNO (70) 17/7210/PNO (119) 18/5067/PNO (94) 19/1952/PNO (94) 19/5403/FUL (43) | NEW BARNET TOWN CENTRE | 2022-23: 137 | 137 | 137
PROPOSED ALLOCATION | Meritage Centre, NW4 4JT | Hendon | Hendon | Call for sites | BRENT STREET TOWN CENTRE | 2027-28: 73 | 73 | 73
CONSENT | 912 - 920 High Road, N12 9RW | Woodhouse | Woodhouse | 20/1360/FUL | NORTH FINCHLEY TOWN CENTRE | 2025-26: 24 | 24 | 24
CONSENT | Britannia House, 960 High Road, N12 9RY | Woodhouse | Woodhouse | 17/6593/FUL 18/5483/FUL (2) | NORTH FINCHLEY TOWN CENTRE | 2023-24: 23 | 23 | 23
PROPOSED ALLOCATION | Mill Hill East Station NW7 1BS | Totteridge & Woodside | Mill Hill | Call for sites | MILL HILL EAST AREA | 2032-33: 60; 2033-34: 67 | 127 | 127
CONSENT | Land Adjacent to Finchley Memorial Hospital | Woodhouse | Woodhouse | 20/4343/OUT | OTHER SITES | 2027-28: 130 | 130 | 130
PROPOSED ALLOCATION | Mill Hill Library | Totteridge & Woodside | Mill Hill | Council Assets Disposal Programme | MILL HILL TOWN CENTRE | 2027-28: 10 | 10 | 10
UNDER CONSTRUCTION | Barnet House, 1255 High Road, N20 0EJ | Totteridge & Woodside | Totteridge | 21/3726/FUL | WHETSTONE TOWN CENTRE | 2024-25: 130; 2025-26: 130 | 260 | 260
PROPOSED ALLOCATION | New Barnet Gasholder, EN4 9SH | East Barnet | East Barnet | Call for sites | NEW BARNET TOWN CENTRE | 2029-30: 100; 2030-31: 101 | 201 | 201
PROPOSED ALLOCATION | North London Business Park, N11 1NP | Brunswick Park | Brunswick Park | 15/07932/OUT | OTHER SITES | 2026-27: 360; 2027-28: 190; 2028-29: 200; 2029-30: 300; 2030-31: 300 | 1350 | 1350
PROPOSED ALLOCATION | Osidge Lane Community Halls, N14 5DU | Brunswick Park | Brunswick Park | Council Assets Disposal Programme | OTHER SITES | 2028-29: 16 | 16 | 16
COMPLETED | Edelman House 1238 High Road N20 0LH | Totteridge & Woodside | Totteridge | 17/6853/PNO | WHETSTONE TOWN CENTRE | 2022-23: 26 | 26 | 26
SITE CLEARED | Victoria Quarter - The Former East Barnet Gas Works | East Barnet | East Barnet | 16/7601/FUL | NEW BARNET TOWN CENTRE | 2025-26: 180; 2026-27: 191 | 371 | 371
SITE CLEARED | Salvation Army Hall, Albert Road, EN4 9SH | East Barnet | East Barnet | 17/5522/FUL | NEW BARNET TOWN CENTRE | 2024-25: 39 | 39 | 39
PROPOSED ALLOCATION | Osidge Library and Health Centre, N11 1EY | Brunswick Park | Brunswick Park | Council Assets Disposal Programme | OTHER SITES | 2029-30: 10 | 10 | 10
PROPOSED ALLOCATION | Park House 16 High Rd N2 9PJ | East Finchley | East Finchley | Council Assets Disposal Programme | EAST FINCHLEY TOWN CENTRE | 2027-28: 19 | 19 | 19
COMPLETED | Friern Court | Whetstone | Totteridge | Barnet Homes 17/5615/FUL 20/2339/FUL | OTHER SITES | 2022-23: 11 | 11 | 11
PROPOSED ALLOCATION | PDSA, NW4 4JU | Hendon | Hendon | Call for sites | BRENT STREET TOWN CENTRE | 2027-28: 32 | 32 | 32
COMPLETED | Whetstone Delivery Office, 14 Oakleigh Road North, N20 9FJ | Totteridge & Woodside | Totteridge | 19/3523/FUL | WHETSTONE TOWN CENTRE | 2021-22: 41 | 0 | 41
UNDER CONSTRUCTION | 70-84 and Land R/O Oakleigh Road North, N20 9EZ | Totteridge & Woodside | Totteridge | 19/1950/FUL | WHETSTONE TOWN CENTRE | 2022-23: 57; 2023-24: 50 | 107 | 107
CONSENT | Oak Lodge, 54 The Bishops Avenue, N2 0BE | Garden Suburb | Finchley Church End | 19/5453/FUL | OTHER SITES | 2025-26: 30 | 30 | 30
UNDER CONSTRUCTION | 6 Barons Court, 56 The Bishops Avenue | Garden Suburb | Finchley Church End | 21/0263/FUL | OTHER SITES | 2023-24: 109 | 109 | 109
PROPOSED ALLOCATION | Philex House 110-124 West Hendon Broadway NW9 7DW | West Hendon | West Hendon | Call for sites/UDP | MAJOR THOROUGHFARE | 2027-28: 22 | 22 | 22
SITE CLEARED | Development Site North of 215 at Former 217 to 223 High Road, N2 8AN | East Finchley | East Finchley | 19/1346/FUL | EAST FINCHLEY TOWN CENTRE | 2026-27: 20 | 20 | 20
CONSENT | 183 Victoria Road, EN4 9PA | East Barnet | East Barnet | 19/3313/FUL | NEW BARNET TOWN CENTRE | 2023-24: 15 | 15 | 15
PROPOSED ALLOCATION | Public Health England NW9 5EQ | Colindale South | Colindale | Call For Sites | COLINDALE GROWTH AREA | 2028-29: 131; 2029-30: 130; 2030-31: 130 | 391 | 391
PROPOSED ALLOCATION | Ravensfield House The Burroughs NW4 4BT | Hendon | Hendon | Call for sites | BRENT STREET TOWN CENTRE | 2027-28: 90 | 90 | 90
PROPOSED ALLOCATION | Sainsbury's, East Barnet Road | East Barnet | East Barnet | New Barnet Town Centre Strategy | NEW BARNET TOWN CENTRE | 2029-30: 100; 2030-31: 99 | 199 | 199
PROPOSED ALLOCATION | Tally Ho Triangle, High Rd, Ballards Lane & Kingsway, North Finchley N12 0GA/0BP | West Finchley | West Finchley | North Finchley SPD | NORTH FINCHLEY TOWN CENTRE | 2028-29: 103; 2029-30: 102 | 205 | 205
CONSENT | 12 - 18 High Road, N2 9PJ | East Finchley | East Finchley | 16/2351/FUL 18/5822/FUL | EAST FINCHLEY TOWN CENTRE | 2023-24: 24 | 24 | 24
COMPLETED | Ann Summers Lane | West Finchley | Woodhouse | Barnet Homes 18/4200/FUL | OTHER SITES | 2022-23: 14 | 14 | 14
PROPOSED ALLOCATION | Tesco Coppetts Centre Colney Hatch Lane N12 0SH | Friern Barnet | Coppetts | Call for sites | MAJOR THOROUGHFARE | 2027-28: 97; 2028-29: 100; 2029-30: 100; 2030-31: 100 | 397 | 397
PROPOSED ALLOCATION | Tesco, 21-29 Ballards Lane N3 1XP | West Finchley | West Finchley | Finchley Church End town centre strategy | FINCHLEY CENTRAL TOWN CENTRE | 2029-30: 100; 2030-31: 70 | 170 | 170
CONSENT | 231 Colney Hatch Lane N11 3DG | Friern Barnet | Coppetts | 20/1610/FUL | OTHER SITES | 2026-27: 104; 2027-28: 100 | 204 | 204
PROPOSED ALLOCATION | The Burroughs Carpark NW4 4AR | Hendon | Hendon | Call for sites | HENDON CENTRAL TOWN CENTRE | 2028-29: 21 | 21 | 21
CONSENT | Land Adj To 114 Coppetts Road | Friern Barnet | Coppetts | 22/1308/FUL | OTHER SITES | 2026-27: 15 | 15 | 15
PROPOSED ALLOCATION | Usher Hall The Burroughs NW4 4HE | Hendon | Hendon | Call for sites | BRENT STREET TOWN CENTRE | 2030-31: 9 | 9 | 9
PROPOSED ALLOCATION | Watchtower House & Kingdom Hall The Ridgeway NW7 1RS | Totteridge & Woodside | Mill Hill | 22/0649/FUL | MILL HILL EAST AREA | 2025-26: 184 | 184 | 184
PROPOSED ALLOCATION | Watford Way & Bunns Lane NW7 2EX | Mill Hill | Mill Hill | Call for sites | MAJOR THOROUGHFARE | 2034-35: 50; 2035-36: 55 | 105 | 105
PROPOSED ALLOCATION | Woodside Park Station East N12 8RT | Whetstone | Totteridge | Call for sites | PUBLIC TRANSPORT INFRASTRUCTURE | 2026-27: 95 | 95 | 95
CONSENT | 45 - 47 Friern Barnet Road London N11 3EG | Friern Barnet | Coppetts | 21/6002/FUL | OTHER SITES | 2026-27: 32 | 32 | 32
CONSENT | 1-13 Cricklewood Lane, NW2 2DQ | Childs Hill | Childs Hill | 18/6353/FUL | CRICKLEWOOD GROWTH AREA | 2025-26: 70; 2026-27: 75 | 145 | 145
0
[5 empty] | TOTAL MAJORS | 1938 | 1244 | 2039 | 2547 | 2401 | 3296 | 4317 | 4206 | 4693 | 3446 | 2559 | 1902 | 1498 | 1438 | 1341 | 186 | 37113 | 38865
[5 empty] | SMALL SITES | 230 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 342 | 5130 | 5018
0
[5 empty] | TOTAL + SMALL SITES | 2168 | 1586 | 2381 | 2889 | 2743 | 3638 | 4659 | 4548 | 5035 | 3788 | 2901 | 2244 | 1840 | 1780 | 1683 | 528 |  | 43883
0
0
0

## Graph Calculation Local Plan
| 2000/01 | 2001/02 | 2002/03 | 2003/04 | 2004/05 | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 | 2010/2011 | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36
Past Completions | 1264 | 389 | 804 | 1766 | 1306 | 1233 | 1329 | 1418 | 1381 | 1496 | 1139 | 1469 | 1409 | 1081 | 1464 | 1735 | 2227 | 2360 | 2229 | 2009 | 2369 | 2168
Projected Completions | 2022/23: 1586; 2023/24: 2381; 2024/25: 2889; 2025/26: 2743; 2026/27: 3638; 2027/28: 4659; 2028/29: 4548; 2029/30: 5035; 2030/31: 3788; 2031/32: 2901; 2032/33: 2244; 2033/34: 1840; 2034/35: 1780; 2035/36: 1683
Cumulative Projected Completions | 2022/23: 1586; 2023/24: 3967; 2024/25: 6856; 2025/26: 9599; 2026/27: 13237; 2027/28: 17896; 2028/29: 22444; 2029/30: 27479; 2030/31: 31267; 2031/32: 34168; 2032/33: 36412; 2033/34: 38252; 2034/35: 40032; 2035/36: 41715
London Plan Target |  |  |  |  | 890 | 890 | 890 | 890 | 2055 | 2055 | 2055 | 2255 | 2255 | 2255 | 2255 | 2349 | 2349 | 2349 | 2349 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364 | 2364
Cumulative Target | 2022/23: 2364; 2023/24: 4728; 2024/25: 7092; 2025/26: 9456; 2026/27: 11820; 2027/28: 14184; 2028/29: 16548; 2029/30: 18912; 2030/31: 21276; 2031/32: 23640; 2032/33: 26004; 2033/34: 28368; 2034/35: 30732; 2035/36: 33096
MONITOR - No. dwellings above or below cumulative target | 2022/23: -778; 2023/24: -761; 2024/25: -236; 2025/26: 143; 2026/27: 1417; 2027/28: 3712; 2028/29: 5896; 2029/30: 8567; 2030/31: 9991; 2031/32: 10528; 2032/33: 10408; 2033/34: 9884; 2034/35: 9300; 2035/36: 8619
MANAGE - Housing requirement taking account of past/projected completions | 2022/23: 3142; 2023/24: 3125; 2024/25: 2600; 2025/26: 2221; 2026/27: 947; 2027/28: -1348; 2028/29: -3532; 2029/30: -6203; 2030/31: -7627; 2031/32: -8164; 2032/33: -8044; 2033/34: -7520; 2034/35: -6936; 2035/36: -6255