Fire safety and the council’s response to the Grenfell Tower tragedy
Briefing Update for Housing and Growth Committee – June 2020

1	Governance
Housing and Growth Committee requested quarterly updates on progress with fire safety works within the borough. Oversight of the project is provided by a fire safety board comprising officers from across the council and partners.
Officer contact: Adam Driscoll - Commissioning Lead for Growth adam.driscoll@barnet.gov.uk

2	Council Housing
2.1	The fire safety delivery programme for Council housing stock is progressing well following a period of re-programming to incorporate all elements of the investment programme approved by committee:
Item	Cost
Granville Road cladding removal, recladding and associated costs	£5,922,900
Category 1 High Priority works	£9,220,433
Additional fire safety works to high rise buildings (Category 2 and 3a works)	£12,656,667
Installation of sprinklers to High Rise blocks with 2 stairwells	£3,220,000
Installation of sprinklers to sheltered housing blocks	£2,330,000
Installation of sprinklers to hostels	£150,000
Works to low and medium rise blocks (Inc. undertaking of type 3 FRA’s and any urgent arising works	£7,900,000
Replacement of composite fire doors	£10,500,000
Total	£51,900,000

Progress on fire safety measures to date:
2.2	Granville Road Recladding - complete.
2.3	Category 1 High Priority Works - Good progress including communal areas of high-rise blocks (Whitefields, Grahame Park and Silk House & Shoelands). However, recent delays caused by COVID-19 impeded access to properties and sourcing of materials, mainly affecting Grahame Park, Silk House & Shoelands where completion dates have moved back to Q2 2020/21.
2.4	Additional fire safety works (category 2 and 3a) - Works at Longford Court only saw minor disruption due to COVID-19; communal elements continued without the need to access homes. Whilst site setup works at Prospect and Norfolk tower blocks in East Finchley commenced in March 2020.
2.5	Installation of sprinklers to blocks of flats with 10 or more floors and 2 or more stairwells - These are still scheduled for 2020/21 and 2021/22; including the three tower blocks at Granville Road where work is due in July 2020.
2.6	Installation of sprinklers to sheltered housing blocks and hostels - Most works are scheduled for 2022/23 and 2023/24, however consideration is being given to accelerating the installation at certain schemes where other disruptive works are scheduled as part of the wider capital investment programme. This applies to sheltered housing at Vale Court and the hostel at Friern Barnet Road.
2.7	There are delays at Vale Court due to Covid-19; with resident safety and shielding against Covid-19 prioritised over implementation of the works, although the design process for these fire safety works are proceeding.
2.8	At St John’s sheltered housing block, incorporation of fire safety works into the wider project that includes a new heating system and electrical upgrades was due to commence in late April 2020, however prospective tenderers are unable to attend site to review the works; the tender period is extended to July 2020.
2.9	Works to low and medium rise blocks (incl. Type 3 Fire Risk Assessments and any urgent arising works) - Expert consultants are undertaking in depth FRAs and any urgent works actioned as a priority, with other observations forming part of a longer term planned programme of improvements. While 150 surveys have been undertaken, the urgent works halted in March due to limited access to properties; but once safe to do so, this programme will recommence.
2.10	Replacement of composite fire doors – Of 5000 “glass reinforced polyester” (GRP) composite fire doors installed in homes managed by Barnet Homes. Updated risk assessments informed the proposed replacement programme and discussions with the contractors who supplied and fitted the doors. Agreement has been reached with the contractor that faulty doors will be replaced at the contractor’s expense and liability resolved through independent adjudication when the work is finished. Work on this programme continues.
2.11	Whitefields Estate - tower block cladding system – The three blocks (Clare, Norden and Whychcote Point), fitted with High-Pressure Laminate (HPL) are due to be demolished in 2023. After expert advice the cladding and non-combustible insulation backing is deemed safe. A programme of work to improve the front doors to flats and fire alarm warning systems is underway.
2.12	Willow House Fire - Works are underway and the project progressed well until issues with the integrity of the block and beam flooring surfaced. Consultants are investigating the issues and will make proposals for rectification. These works are likely to result in increased costs and delay the project by 16 weeks. This has further exacerbated delays caused by COVID-19, although works were due to recommence onsite before the end of June 2020.
2.13	Large Panel System buildings - Surveys for such works are complex and invasive, requiring tenants to be decanted as concrete must be removed to allow visual inspection alongside calculations to assess structural integrity against an internal gas explosion. The gas distributor, Cadent, have sought reassurance from Barnet Homes that its LPS buildings are safe to retain piped gas, a set of precautionary risk mitigation measures for blocks at West Hendon and Dollis Valley is currently being implemented.
2.14	As the recommendation for next steps at Silk House recommended the removal of the piped gas supply to the block, the gas supply to all properties was disconnected in June 2019 whilst replacement communal heating is installed. With no gas being supplied, Cadent do not have concerns about the building, but Barnet Homes have taken additional precautionary measures to prevent accidental loading by not permitting portable gas heaters in high rise buildings; with tenancy audits ensuring portable gas appliances are not being used.
2.15	Surveys have been completed for Marsh Drive and blocks in Dollis Valley that confirm they do not meet the required standard. It was agreed with Cadent to work towards decant of Marsh Drive, and piped gas decommissioning at relevant Dollis Valley blocks, by October 2020. This agreement is based on Barnet Homes implementing safety measures that include installing gas safety monitoring equipment in each flat, removal of gas appliances and monthly safety checks of the gas boilers. Gas safety monitoring is now installed in all but 6 of the 358 homes, for which a legal process to gain access is in progress.
2.16	Cadent have acknowledged Covid-19 impacts and agreed the potential for extension to February 2021 for decanting Marsh Drive; although both parties have agreed to endeavour to achieve the October 2020 timescale. At the Dollis Valley blocks, where decant is phased over five years, a new electric heating system will be installed by October 2020, with work due to commence in July.

Registered Providers
3.1	Of three Housing Associations with confirmed ACM cladding on blocks, works at one are complete, and both others are due to complete by September 2020, for one of these providers this includes the 3-months delay due to Covid-19.
3.2	In addition, the further provider with a block held through a lease in Colindale, has an up to date fire risk assessment and the freeholder is responsible for replacing the cladding. The owner of the building has recently confirmed they plan to replace the cladding with fibre cement panels. The owners have been liaising with the council’s building control team and have applied to MHCLG for funding to meet the replacement costs of the cladding.

Private Sector buildings (residential and commercial)

  1. There continues to be two privately owned blocks higher that 18 meters with failed ACM cladding that the council’s building control team are in touch with; both have confirmed plans to replace the cladding and have advised that they have requested funding from the Government to assist with replacement.
  2. An additional high-rise block identified and inspected in September 2019 was served with an Improvement Notice by LFEPA, inspected by Barnet and an appointed Joint Inspection Team (JIT) who reported back to the building owners and the Fire Authority, and subsequently the Fire Authority have confirmed that significant improvements have been completed to the building and their initial notice has been complied with. A revised Fire Risk Assessment is in the process of being written and follow up works planned. The Council are awaiting legal advice prior to taking any action under the Housing Act 2004.

  1. Lastly, following wider concerns about the safety of some non-ACM systems, the Government further exercise to identify external wall covering on all buildings higher than 18 meters in their area is underway. The review is seeking to identify the type of insultation used for each building and external features such as balconies. This exercise is anticipated to complete in July 2020, with any concerns identified to be raised with building owners; the council will work with the Government and LFEPA to ensure the ongoing safety of residents.

Next Update:
5.1	Housing and Growth Committee will be provided with its next quarterly briefing update by October 2020 covering programme updates from Q2 2020.