	Housing and Growth Committee / 24 November 2020
Title	Fire Safety – progress update
Report of	Chairman of Housing and Growth Committee
Wards	All
Status	Public
Urgent	No
Key	No
Enclosures	Appendix A – Fire Safety Briefing update / Appendix B – Action Plan Tracker
Officer Contact Details	Adam Driscoll, Commissioning Lead - Growth. / 020 8359 4922 – Adam.Driscoll@barnet.gov.uk / Elliot Sweetman, Group Director of Operations and Property, Barnet Homes. / 020 8359 5261 – Elliott.Sweetman@barnethomes.org / Belinda Livesey, Group Manager, Environmental Health, Re / 020 8359 7438 - Belinda.Livesey@barnet.gov.uk / Helen Philips, Affordable Housing Liaison Officer, Re / 020 8359 4861 - Helen.Phillips@Barnet.gov.uk / Michael Keown, Building Control Manager, Re / 020 8359 4879 - Michael.Keown@Barnet.gov.uk

Summary
This report is to provide an update on the progress of fire safety works within the borough since the last report to Housing and Growth Committee, submitted to the 14 September 2020 meeting. It notes the progress of private sector blocks towards securing the funding to enable remedial works to take place.
Officers Recommendations
That the Committee notes the updates since the previous report.

WHY THIS REPORT IS NEEDED
  1. Reports have previously been made to Housing and Growth Committee with the most recent report in September 2020 noting the progress of Barnet Homes with high priority fire safety works as well as the expanded programme of work. It also noted progress by Registered Providers, together with coordination work on behalf of government to identify unsafe cladding in the private sector.
# NATIONAL CONTEXT UPDATES
  1. On 4th June 2020 the government launched its £1 billion building safety fund to help address one of the barriers to progression of remedial action, and the registration process for applying to this fund ended on 31st July 2020.

  1. Of the two private sector blocks where funding was sought, each have provided updates:
- One block has confirmed that grant funding has been secured.
- The other block was initially unsuccessful with their bid but have secured a revised recommended tender for necessary remedial works and are making a further application to the government for funds (both ACM and non-ACM).
  1. There are no further updates in terms of the national context since the September report.
# KEY LOCAL CONTEXT UPDATES
  1. Full details of the local context are set out in Appendix A, with progress against the defined action plan set out in Appendix B.
  1. The programme of remedial works planned by the council is continuing for those properties where the council is responsible for improvements. The only key update to the programme to report this quarter is that the completion of the High Priority Works, referenced in Appendix A paragraph 3.3, have been pushed back to Q3 2020 due to ongoing access and material sourcing (COVID-19 related) delays. Appendix A also notes progress towards other milestones including the sprinkler works progression to tender stage, and completion of a further 210 surveys relating to works to low and medium rise properties. Lastly, the number of buildings likely to be ‘in scope’ for new fire safety regulations has reduced slightly to 22 blocks.

  1. Works to remedy Registered Social Landlord (RSL)-owned blocks that were due for completion in September have been confirmed as complete in one case and due for completion by end of November in the second case. Subject to such confirmation, that leaves just the one further site, held through a lease, where responsibility for remediation sits with the freeholder.
  1. There are three private sector blocks where remedial action is being monitored and following initial investigation the landowners have put in place interim safety measures. Assessment and enforcement in relation to these blocks have been coordinated with the London Fire and Emergency Planning Authority (LFEPA) to ensure they are clear about their responsibilities and the actions required to deliver permanent fire safety measures. The council continues to coordinate with MHCLG around intended start and completion dates for the remedial works, and as noted in paragraph 1.2, necessary funding has been secured or sought to resolve issues in relation to two blocks.
REASONS FOR RECOMMENDATIONS
  1. The council needs to ensure the safety of residents living in Barnet by delivering either directly or indirectly the fire safety works programme.
  1. Engagement with landowners of housing stock outside of the council’s control continues to be a mixed picture but for the key sites, works are being pursued and in some cases are now expected to soon get underway; however if the commitments made to date are not met, then enforcement will take place.
ALTERNATIVE OPTIONS CONSIDERED AND NOT RECOMMENDED
  1. This is an update to the September 2020 report.
POST DECISION IMPLEMENTATION
  1. The council will continue to coordinate delivery of the agreed action plan in Appendix B.
  1. Barnet Homes will continue to progress the council’s programme of works to improve fire safety within its own stock.
  1. The council will continue to update MHCLG and will proceed to arrange enforcement action to ensure compliance and remediation where required.
IMPLICATIONS OF DECISION
  1. Corporate Priorities and Performance
    1. This paper is an update to the September 2020 Report.
  1. Resources (Finance & Value for Money, Procurement, Staffing, IT, Property, Sustainability)
    1. There are no changes to resources since the September 2020 report.
  1. Social Value
    1. There are no changes to social value considerations since the September 2020 report.
  1. Legal and Constitutional References
    1. The council’s Constitution Article 7.5 Responsibility for Functions, states that the Housing and Growth Committee is responsible for housing matters including housing strategy, homelessness, social housing and housing grants, together with the commissioning of environmental health functions for private sector housing.
    1. The Housing Act 2004 (sections 3 and 4) require local authorities to keep the housing conditions in their area under review and to inspect the same if it considers a category 1 or 2 hazard (as defined by the Act) exists and gives powers to intervene where they consider housing conditions to be in breach of the same.
  1. Risk Management
    1. There are no changes to risk management since the September 2020 report.
  1. Equalities and Diversity
    1. There are no changes to compliance with the equalities and diversity duties since the September 2020 report.
  1. Corporate Parenting
    1. There are no changes to the relationship to corporate parenting since the September 2020 report
  1. Consultation and Engagement
    1. There are no changes to consultation and engagement since the September 2020 report.
  1. Insight
    1. There are no changes to insight since the September 2020 report.
BACKGROUND PAPERS
  1. Housing and Growth Committee – 14th September 2020 – Item 9: Fire Safety – progress update
# https://barnet.moderngov.co.uk/ieListDocuments.aspx?CId=696&MId=10226&Ver=4
  1. Housing Committee - 1 April 2019 – Item 8: Housing Strategy.
# https://barnet.moderngov.co.uk/documents/s51891/Housing%20Strategy.pdf
  1. Housing Committee – 14th January 2019 – Item 10: Fire Safety – progress update
# https://barnet.moderngov.co.uk/documents/s50421/Fire%20Safety%20progress%20update.pdf
  1. Housing Committee 21st June 2018 – Item 8 – Fire Safety Update
# http://barnet.moderngov.co.uk/ieListDocuments.aspx?CId=699&MId=9486&Ver=4
  1. Housing Committee 23rd October 2017 – Item 9 – Fire Safety Update
# http://barnet.moderngov.co.uk/ieListDocuments.aspx?CId=699&MId=9237&Ver=4
  1. Housing Committee 26th June 2017 – Item 7 – Response to Grenfell Tower Fire
# http://barnet.moderngov.co.uk/ieListDocuments.aspx?CId=699&MId=9236&Ver=4
REPORT CLEARANCE CHECKLIST
# (Removed prior to publication and retained by Governance Service)
# Note: All reports must be cleared by the appropriate Committee Chairman, Chief Officer, Legal, Finance and Governance as a minimum. Report authors should also engage with subject matter experts from other service areas where this is required (e.g. procurement, equalities, risk, etc.). The name and date that the chairman or officer has cleared the report must be included in the table below or the report will not be accepted.
# Legal, Finance and Governance require a minimum of 5 working days to provide report clearance. Clearance cannot be guaranteed for reports submitted outside of this time and your report is likely to be withdrawn from the agenda and deferred to the next scheduled meeting.
# Author to complete TABLE BELOW:
Who	Clearance Date	Name
Committee Chairman	16/11/2020	Cllr Richard Cornelius
Chief Officer	16/11/2020	Luke Ward / Stephen McDonald
HB Public Law	13/11/2020	Jennifer Affie
Finance	07/11/2020	Damian Pantling
Governance	09/11/2020	Abigail Lewis