Housing & Growth Committee

Fire safety update – April 2021

1.	Summary

1.1	This report provides an update on the progress of fire safety works within the borough since the last report to Housing & Growth Committee in November 2020.

# 2. National context updates
  1. The government has banned combustible materials in the external walls of high-rise residential buildings of 18 metres and over, and following a review into its effectiveness, is now consulting on extending the ban significantly further, including lowering the 18 metres height threshold to 11 metres.

  1. In the March 2020 budget, the government announced that it would provide £1 billion in 2020/21 to support the remediation of unsafe non-ACM cladding system on residential buildings 18 metres and over in both the private and social housing sectors. On 26 May 2020, the Building Safety Fund was launched with registration open between 1 June 2020 and 31 July 2020.

  1. Two private sector blocks in Barnet registered for funding:
- One block has confirmed that funding was secured for recladding works.
- The second block has put in a planning and building control application for recladding works.

  1. On 17 December 2020, the government announced a new £30 million Waking Watch Relief Fund to pay for the installation of alarms to remove or reduce the reliance on Waking Watch in buildings over 18 metres with unsafe cladding systems.
# 3. Key local context updates
# 3.1 Following a Motion at Council on 19 January 2021, Members pledged support to Inside Housing’s “10 steps to End our Cladding Scandal”.
# 3.2 The council is in regular contact with the local housing sector. On 17 March 2021, we held a “listening” event with representatives of local cladding groups to hear their concerns about cladding and fire safety; as well as clarify the council’s various roles in relation to cladding and fire safety. A separate meeting was held with the large Registered Providers (RPs) in the borough. Legislative updates and information about government funding is shared.
# 3.3 The programme of remedial works planned by the council is continuing for those properties where the council is responsible for improvements. Key updates include some delays to the completion of High Priority Works due to Covid-19. Whilst additional fire safety works at Prospect and Norfolk tower blocks are due for completion by Q1 21/22.
# 3.4 Sprinkler works, including at the three tower blocks at Granville Road are due to commence in Q1 21/22. Lastly, the number of buildings likely to be ‘in scope’ for new fire safety regulations has reduced slightly to 21 blocks. Resources have been identified and a provision made within the updated Housing Revenue Account Business Plan due to be reviewed by the committee in May 2021.

3.5	Of the three Registered Providers (RPs) with confirmed ACM or non-ACM (but combustible) cladding on blocks:
- One RP has completed all works to the block affected; all properties were rented, and costs were not rechargeable.
- A second RP has completed the cladding replacement works with no recharges to leaseholders. This RP has planned further works to remove all combustible material from the balconies and terraces and is waiting for the outcome of their bid from the Building Safety Fund. They have reported that some leaseholders have managed to complete on sales without a full EWS1 certificate.
- A third RP, with a block held through a lease, has an up-to-date fire FRA and the freeholder is responsible for replacing the cladding. The freehold was sold in September 2020 and received funding approval in October 2020. The owner of the building has confirmed they plan to replace the cladding with fibre cement panels. Supplementary information submitted to the planning team has been approved. The block is monitored by building control.

3.6	The two private sector blocks with ACM cladding have plans to replace the cladding and have requested funding from the government to assist with replacement. In both cases, a planning and building control application has been submitted for the proposals with work due to start following approvals.

3.7	An additional high-rise block, identified and inspected in September 2019, was served with an Improvement Notice by the Fire Authority. It was also inspected by Barnet and the LGA’s Joint Inspection Team (JIT) who reported back to the building owners and the Fire Authority. Following liaison with the council and the Fire Authority, extensive work has been and is being completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council is in the process of taking legal action under the Housing Act 2004.
# 3.8 Full details of the local context are set out in Appendix A, with progress against the defined action plan set out in Appendix B.

APPENDIX A: Fire safety and the council’s response to the Grenfell Tower tragedy (March 2021)
# 1. Introduction

1.1	This report provides a progress update on fire safety issues in Barnet, including progress on the agreed package of fire safety improvement works for council properties managed by Barnet Homes, as well as activity in relation to relevant Registered Provider and Private Sector housing stock.
# 2. Building a Safer Future (Building Safety Bill and Fire Safety Bill)

2.1	Building a Safer Future (BSF) is a government-led initiative in response to the Grenfell Tower tragedy. It is a framework within which the shortcomings identified in the post-Grenfell review of Building Regulation and Fire Safety can be addressed. These shortcomings include the way high-rise residential buildings are built and managed. BSF is also intended to deal with situations where residents may raise concerns about the safety of their buildings, which they may feel are not taken seriously by their landlord.

2.2	Two key pieces of legislation support this initiative – the Building Safety Bill and the Fire Safety Bill, both of which are expected to receive Royal Assent in the second half of 2021. The new Building Safety Regulator, working under the responsibility of the Health and Safety Executive and with responsibility for ‘high risk’ / ‘in-scope’ buildings (e.g. residential blocks over 18 metres, but other criteria may be defined through subsequent statutory instruments) is unlikely to be fully operational until 2023/24.

2.3	The Fire Safety Bill will amend the Fire Safety Order 2005 to clarify that the responsible person or duty-holder for multi-occupied, residential buildings must manage and reduce the risk of fire for:
- the structure and external walls, including cladding, balconies and windows
- entrance doors to individual flats that open into common parts.

This clarification will empower fire and rescue services to take enforcement action and hold building owners to account if they are not compliant.

  1. This means an expert Building Safety Manager will need to be appointed for each block, a regular inspection regime put in place for fire doors, as well as wider reinforcement of better management and increased accountability, as detailed in the Hackitt report.

  1. The new regulatory framework is designed to make building safety issues transparent to all parties involved and reinforce responsibilities. This includes a role for residents in keeping their buildings safe for themselves and their neighbours. The buildings in scope are currently those 18 metres or higher.

  1. Following the consultation and formal introduction of the Bills it is inevitable that there will be additional requirements for other enhanced aspects of building and fire safety and ongoing management of our buildings and the wider housing stock within the borough. It is therefore likely that additional costs and responsibilities will be identified as this process continues.

# 3. Council Housing

3.1	The fire safety delivery programme for council housing stock is progressing well following a period of re-programming to incorporate all elements of the investment programme approved by committee:

Item	Cost
Granville Road cladding removal, recladding and associated costs	£5,922,900
Category 1 High Priority works	£9,220,433
Additional fire safety works to high rise buildings (Category 2 and 3a works)	£12,656,667
Installation of sprinklers to High Rise blocks with 2 stairwells	£3,220,000
Installation of sprinklers to sheltered housing blocks	£2,330,000
Installation of sprinklers to hostels	£150,000
Works to low and medium rise blocks (Inc. undertaking of type 3 FRA’s and any urgent arising works	£7,900,000
Replacement of composite fire doors	£10,500,000
Total	£51,900,000

3.2	Granville Road Recladding - complete.

3.3	Category 1 High Priority Works - Good progress continues to be made, including communal areas of high-rise blocks (Whitefields, Grahame Park and Silk House & Shoelands). However, further delays caused by Covid-19 have affected progress at Grahame Park and Silk House & Shoelands where completion was achieved in Q4 2020/21. Whitefields was also completed in Q4 2020/21, including works to improve the front doors to flats and fire alarm warning systems.

3.4	Additional fire safety works (Category 2 and 3a) - Works at Longford Court suffered minor disruption only due to Covid-19 and works are due to complete in mid-April. After a later than planned start, works at Prospect and Norfolk tower blocks in East Finchley have progressed well and completion is scheduled for Q1 2021/22.

3.5	Installation of sprinklers to blocks of flats with 10 or more floors and 2 or more stairwells - These are still scheduled for 2021/22; including the three tower blocks at the Granville Road Estate in NW2 where consultation on the retendered works is complete and works scheduled to commence in Q1 2021/22.

3.6	Installation of sprinklers to sheltered housing blocks and hostels - Most works are scheduled for 2022/23 and 2023/24; however consideration is being given to accelerating the installation at certain schemes where other disruptive works are scheduled as part of the wider capital investment programme. Such works were prioritised at Vale Court sheltered scheme and Friern Barnet hostel but were impacted by Covid-19. However, these fire safety works are now essentially complete.

3.7	Fire safety works at St John’s Close sheltered housing block, incorporating other investment work including a new heating system plus electrical upgrades has started on site and will be completed during Q3 2021/22, following some Covid-19 delays.

3.9	Works to low and medium rise blocks (incl. Type 3 Fire Risk Assessments (FRAs) and any urgent arising works) - Expert consultants are undertaking in-depth FRAs and any urgent works actioned as a priority, with other observations forming part of a longer-term planned programme of improvements. Almost 850 surveys have been undertaken with the remainder (approx. 150) scheduled for completion by mid-May 2021.

3.10	Replacement of composite fire doors – There are 5000 “glass reinforced polyester” (GRP) composite fire doors installed in homes managed by Barnet Homes. Updated risk assessments informed the proposed replacement programme and discussions with the contractors who supplied and fitted the doors. Agreement has been reached with the contractor that faulty doors will be replaced at the contractor’s expense and liability resolved through independent adjudication when the work is finished. Work on this programme continues with over 1000 door installations completed by the end of Q4 2020/21.

3.11	Whitefields Estate - tower block cladding system – The three blocks (Clare, Norden and Whychcote Point) fitted with High-Pressure Laminate (HPL) are due to be vacated by 2024, a year later than previously forecast. An extensive programme of work to improve the front doors to flats, communal doors, other compartmentation related upgrade works, and fire alarm warning systems is now complete. After expert advice the cladding and non-combustible insulation backing has been deemed safe but given the delayed vacant possession date of the blocks, Barnet Homes are now seeking further expert advice regarding the approach to mitigating risk at these blocks in the interim.

3.12	Willow House Fire - Works progressed well following the identification of issues with the integrity of the block and beam flooring. Structural works are complete, but there have been significant Covid-19 delays affecting the contractor’s on-site workforce. Leaseholders due to confirm their new kitchen and bathroom layouts were unable to attend as result. Works to homes are complete with residents expected to return by early Q1 2021/22.

3.13	Large Panel System (LPS) buildings - The gas distributor, Cadent, have sought reassurance from Barnet Homes that its LPS buildings are safe to retain piped gas. At Dollis Valley and Silk House & Shoelands piped gas has been removed and at Marsh Drive it is part way through being removed. A set of precautionary risk mitigation measures for blocks at Marsh Drive, Dollis Valley, and Silk House & Shoelands has been implemented.

3.14	A new heating system has been installed at Silk House & Shoelands. At Dollis Valley, where decant is phased, a new electric heating system has been installed. Cadent have acknowledged Covid-19 impacts and agreed an extension to 31 March 2021 for decanting Marsh Drive. Only 2 households remained in occupation in Marsh Drive on 31 March 2021, who both subsequently vacated on 8 April 2021 with the site being secured ready for handover to the developer. Cadent will now complete full decommission of the remaining risers at Dollis Valley and Marsh Drive on 15 April 2021.

 3.15	Responding to changing legislation - Barnet Homes has completed an initial assessment of how the new requirements of the Building Safety Bill and Fire Safety Bill will impact on the council housing stock in Barnet. Following the handover of blocks on the West Hendon estate, it is currently expected that 21 buildings will be considered ‘in-scope’ within the Barnet Homes stock and associated resources have been identified and a provision made within the updated Housing Revenue Account Business Plan due to be reviewed by the committee in May 2021.

# 4. Registered Providers (RPs)

4.1	Of the three RPs with confirmed ACM or non-ACM (but combustible) cladding on blocks, one RP has completed all works to the one block affected; all properties were rented, and costs were not rechargeable. A second RP has completed the cladding replacement works with no recharges to leaseholders. This RP has planned further works to remove all combustible material from the balconies and terraces and is waiting for the outcome of their bid from the Building Safety Fund. They have reported that some leaseholders have managed to complete on sales without a full EWS1 certificate.

4.2	In addition, a third RP, with a block held through a lease, has an up-to-date fire FRA and the freeholder is responsible for replacing the cladding. The freehold was sold in September 2020 and received funding approval in October 2020. The owner of the building has confirmed they plan to replace the cladding with fibre cement panels. Supplementary information submitted to the planning team has been approved. The block is monitored by building control.

4.3	Another RP has seven blocks in Barnet over 18 metres that require fire safety work. Funding has been applied for all eligible blocks and the original contractor on some of the blocks has agreed to replace fire barriers in the relevant blocks and the RP is in ongoing communication with the other contractors regarding remediation works. The RP has also engaged with the warranty providers regarding remediation.

4.4	In March 2021, the above RP plus another RP in the borough attended a meeting with members to discuss various issues including fire safety.

4.5	All large RPs in the borough, including those with buildings over 18 metres, are in regular communication over fire safety of their affordable housing. Information about government funding has been shared with RPs, along with the council’s pledge of support to Inside Housing’s “10 steps to End our Cladding Scandal”.

# 5. Private Sector buildings (residential and commercial)

5.1	There continues to be two privately owned blocks higher than 18 metres with failed ACM cladding that the council’s building control team are in touch with; both have confirmed plans to replace the cladding and have advised that they have requested funding from the government to assist with replacement. In both cases a planning and building control application has been submitted for the proposals with work due to start following approvals.

5.2	An additional high-rise block, identified and inspected in September 2019, was served with an Improvement Notice by the Fire Authority. It was also inspected by Barnet and the LGA’s Joint Inspection Team (JIT), who reported back to the building owners and the Fire Authority. Following liaison with the council and the Fire Authority, extensive work has been and is being completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council is in the process of taking legal action under the Housing Act 2004.

5.3	Following wider concerns about the safety of some non-ACM systems, the government requested a further exercise to identify external wall covering on all buildings higher than 18 metres in their area. The review by building control officers was completed. The council has written to landowners/landlords to seek further information, to identify the type of insultation used for each building and any external features such as balconies, where required, to update the national dataset. The initial exercise completed in May 2020 and the outstanding cases will be followed-up. Work continues with the government and Fire Authority to ensure the ongoing safety of residents. Over recent weeks there have been two sites with ACM cladding referred to the council for follow-up, following the service of notices by the Fire Authority.

Appendix B: Barnet Council Fire Safety Action Plan (March 2021)

1.1	The table below captures only actions that remain ongoing at the time fire safety was last reported to the Housing & Growth Committee, together with any new actions that have arisen.

Action	Status	Notes
Undertake high priority works identified in surveys	Ongoing	High priority works are close to completion, access to some properties and sourcing of materials due to Covid-19 has caused delays.
Work with government and RPs to ensure actions to address any fire safety concerns are addressed	Ongoing	Two RPs with blocks with ACM panels that failed tests have completed the remedial works or are close to completing. One further ‘leased’ building still requires remedial action.
Liaison with owners of blocks with failed ACM cladding	Ongoing	One block has confirmed that funding was secured for recladding works. The second block has put in a planning and building control application for recladding works.
Actions from Fire Risk Assessments for commercial units beneath residential	Ongoing	An extensive review of each commercial premises has been completed, which confirmed suitable arrangements and inspection regimes are in place. Two of 42 properties raised concern and additional enforcement was taken. One surrendered their lease following enforcement and the other complied with the London Fire Brigade inspection and was subsequently considered not to pose further risk. All properties are being monitored as part of the Capita non-managed estate (KPI24c) regime to give ongoing assurance.
Implement the requirements of the Building Safety and Fire Safety Bills	Ongoing	The revised requirements for council and other landowners are being reviewed to ensure measures are in place to deliver full compliance. 21 council buildings are likely to be ‘in-scope’.