Housing & Growth Committee

Fire safety update – June 2021

1.	Summary

1.1	This report provides an update on the progress of fire safety works within the borough since the last update to Housing & Growth Committee in April 2021.

# 2. National updates
2.1	The Fire Safety Bill received Royal Assent on 29 April 2021 and is now an Act of Parliament. The Act amends the Regulatory Reform (Fire Safety) Order 2005 to require all Responsible Persons (e.g. the relevant duty holder) to assess, manage and reduce the fire risks posed by the structure and external walls of the buildings for which they are responsible (including cladding, balconies and windows) and individual doors opening onto common parts of the building.

# 3. Key local updates
# 3.1 The programme of remedial works planned by the council are now practically complete for Category 1 High Priority Works. Whilst additional fire safety works (Category 2 and 3a) will be fully completed by the end June 2021 at Longford Court, Norfolk Close and Prospect Ring.
# 3.2 Sprinkler works at Upper Fosters towers are almost complete and will begin at Granville Road towers at the end of June 2021.
3.3	Of the three Registered Providers (RPs) with confirmed ACM or non-ACM (but combustible) cladding on blocks:

- One RP has completed all works to the block affected; all properties were rented, and costs were not rechargeable.
- A second RP has completed the cladding replacement works with no recharges to leaseholders. This RP has planned further works to remove all combustible material from the balconies and terraces and is waiting for the outcome of their bid from the Building Safety Fund Appeal. They have reported that some leaseholders have managed to complete on sales without a full EWS1 certificate.
- A third RP, with a block held through a lease, has an up-to-date Fire Risk Assessment (FRA) and the freeholder is responsible for replacing the cladding. The freehold was sold in September 2020 and received initial funding approval in October 2020 and is currently waiting for the outcome of a revised bid. The owner of the building has confirmed they plan to replace the cladding with fibre cement panels. Supplementary information submitted to the Planning team has been approved. The block is monitored by Building Control and Environmental Health.

3.4	Contact has been made with the owners of eight potentially high-risk ACM clad blocks and information notices served. Two private sector blocks have plans to replace the cladding and requested funding from the government to assist with replacement. In both cases, a planning and building control application has been submitted for the proposals with work due to start following approvals. One of these has been inspected with the LGAs Joint Inspection Team (JIT) and an Improvement Notice is likely to be required under the Housing Act 2004. The JIT are to submit their inspection report to the council for review.

3.5	An additional high-rise block, identified and inspected in September 2019, was served with an Improvement Notice by the Fire Authority which has since been complied. It was also inspected by the council and JIT who reported back to the building owners and the Fire Authority. Following liaison with the council and the Fire Authority, extensive work has been and is being completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council is in the process of taking legal action under the Housing Act 2004.
# 3.6 Full details of the local context are set out in Appendix A, with progress against the defined action plan set out in Appendix B.

APPENDIX A: Fire safety and the council’s response to the Grenfell Tower tragedy (June 2021)
# 1. Introduction

1.1	This report provides a progress update on fire safety issues in Barnet, including progress on the agreed package of fire safety improvement works for council properties managed by Barnet Homes, as well as activity in relation to relevant Registered Providers (RPs) and Private Sector housing stock.
# 2. Building a Safer Future (Fire Safety Bill and Building Safety Bill)

2.1	Building a Safer Future (BSF) is a government-led initiative in response to the Grenfell Tower tragedy. It is a framework within which the shortcomings identified in the post-Grenfell review of Building Regulation and Fire Safety can be addressed. These shortcomings include the way high-rise residential buildings are built and managed. BSF is also intended to deal with situations where residents may raise concerns about the safety of their buildings, which they may feel are not taken seriously by their landlord. Two key pieces of legislation support this initiative: the Fire Safety Bill and Building Safety Bill.

2.2	The Fire Safety Bill received Royal Assent on 29 April 2021 and is now an Act of Parliament. The Act amends the Regulatory Reform (Fire Safety) Order 2005 to require all Responsible Persons (e.g. the relevant duty holder) to assess, manage and reduce the fire risks posed by the structure and external walls of the buildings for which they are responsible (including cladding, balconies and windows) and individual doors opening onto common parts of the building. It applies to all multi-occupied residential buildings and is not dependent on the height of the building. The intention of the Act is to more readily allow the Fire and Rescue Service to enforce against non-compliance with a Fire Safety Order.

2.3	The Building Safety Bill takes forward the government’s commitment to reform the building safety system set out in BSF. A new Building Safety Regulator will be formed under the responsibility of the Health and Safety Executive (HSE), which will oversee the design, construction and occupation of high-risk buildings (e.g. residential blocks over 18 metres). It is anticipated that the HSE will look to deliver an inspection regime through a ‘competent and registered workforce’ such as that provided by Local Authority Building Control (LABC) services, and the council is preparing for this accordingly. The Bill is likely to be enacted next year.

2.4	The changing legislative framework for fire safety will introduce additional requirements for building safety and the management of our buildings and wider housing stock within the borough. These requirements are being identified through an officer working group and an action plan will be developed.

# 3. Council Housing

3.1	The fire safety delivery programme for council housing stock continues to progress well:

Item	Cost
Granville Road cladding removal, recladding and associated costs	£5,922,900
Category 1 High Priority works	£9,220,433
Additional fire safety works to high rise buildings (Category 2 and 3a works)	£12,656,667
Installation of sprinklers to High Rise blocks with 2 stairwells	£3,220,000
Installation of sprinklers to sheltered housing blocks	£2,330,000
Installation of sprinklers to hostels	£150,000
Works to low and medium rise blocks (Inc. undertaking of type 3 FRA’s and any urgent arising works	£7,900,000
Replacement of composite fire doors	£10,500,000
Total	£51,900,000

3.2	Granville Road Recladding - complete.

3.3	Category 1 High Priority Works - Works to flats and communal areas of high-rise blocks (Whitefields, Grahame Park and Silk House & Shoelands), including works to improve the front doors to flats and fire alarm warning systems, are now practically complete.

3.4	Additional fire safety works (Category 2 and 3a) - These works at Longford Court, Norfolk Close and Prospect Ring will be fully completed by the end of June 2021 with completion slightly impacted by difficulties with access to a small number of properties.

3.5	Installation of sprinklers to blocks of flats with 10 or more floors and 2 or more stairwells – Fire safety works at Granville Road towers are due to begin at the end of June 2021 following a re-tendering exercise and works at the Upper Fosters towers are almost complete except for some difficulties with access to a small number of properties.

3.6	Installation of sprinklers to sheltered housing blocks and hostels - Most works are scheduled for 2022/23 and 2023/24, however consideration is being given to accelerating the installation at certain schemes where other disruptive works are scheduled as part of the wider capital investment programme.

3.7	Fire safety works at St John’s Close sheltered housing block, incorporating other works including a new heating system and electrical upgrades, is on site and will be completed later in 2021 following some Covid-19 delays.

3.8	Works to low and medium rise blocks (incl. Type 3 Fire Risk Assessments (FRAs) and any urgent arising works) - Expert consultants are undertaking in-depth FRAs and any urgent works actioned as a priority, with other observations forming part of a longer-term planned programme of improvements. Almost 900 surveys have been undertaken with the remaining 100 scheduled for completion in June 2021.

3.9	Replacement of composite fire doors – The programme of fire door replacements continues with c.1770 door installations now complete. Agreement has been reached with the contractor for faulty doors to be replaced at the contractor’s expense and liability resolved through independent adjudication when the work is finished. There remains c.1850 doors to replace within that contract and the scheduled completion is September 2021. Another 1400 doors are being replaced through separate arrangements.

3.10	Whitefields Estate - tower block cladding system – The three blocks (Clare, Norden and Whychcote Point) fitted with High-Pressure Laminate (HPL) are due to be demolished in 2024, a year later than previously forecast. The cladding systems on the towers were investigated by third party experts in 2017 and reassessed in 2019. The cladding panels themselves were tested in UKAS accredited laboratories and achieved an acceptable rating of Class B. In addition, a comprehensive package of fire safety improvements has been completed to each block.

3.11	However, given the evolving nature of government guidance relating to high-rise building safety, the recently announced delay in vacating the blocks and our commitment to the safety of our residents, we considered it appropriate to engage a third party expert fire consultant to undertake a reassessment of the cladding system and wider fire safety arrangements of the blocks. Following sample intrusive works, the fire consultant determined that the cladding system should be removed to ensure additional safety for residents. Subsequently, consultants and contractors were mobilised quickly with work starting in the week commencing 10 May 2021 and the work is expected to be completed by October 2021.

3.12	As agreed with the London Fire Brigade, a 24/7 patrol has been put in place for the period of the cladding removal to facilitate a change from a stay put policy to an evacuation strategy in the event of a fire incident. Engagement and communication with residents have been extensive with a number of online resident information and feedback sessions completed and further sessions planned.

3.13	Due to the limited lifespan of the blocks the cladding system will not be replaced, however we will ensure that any remedial works are completed to the blocks as the cladding is removed. We also recognise that without external cladding residents fuel bills will likely increase, so we will undertake energy assessments to understand the impact of removing the cladding and ensure that additional energy costs are reimbursed to residents whilst the blocks remain occupied.

3.14	Willow House Fire - Works progressed well following the identification of issues with the integrity of the block and beam flooring. Structural works are complete, and residents have been able to return while minor making good works are completed.

3.15	Large Panel System (LPS) buildings - The gas distributor, Cadent, has now removed piped gas from Marsh Drive (where we have vacant possession), as well as affected blocks at Silk House/Shoelands and Dollis Valley. With the gas supply decommissioned and other mitigation measures in place, alternative electric heating systems have been installed at the occupied schemes with residents recompensed for additional heating costs.

3.16	A consultant’s report on Holmesdale and Stanhope medium-rise LPS blocks in N11 has determined that risk mitigation measures are necessary here also and these are being progressed accordingly.

3.17	Responding to changing legislation - Barnet Homes has completed an initial assessment of how the new requirements of the Building Safety Bill and Fire Safety Act will impact on the council housing stock in Barnet. Following the handover of blocks on the West Hendon estate, it is currently expected that 21 buildings will be considered ‘in-scope’ within the council stock and associated resources have been identified and a provision made within the updated Housing Revenue Account Business Plan due to be reviewed by the Housing & Growth Committee in June 2021.

# 4. Registered Providers (RPs)

4.1	Of the three RPs with confirmed ACM or non-ACM (but combustible) cladding on blocks, one RP has completed all works to the one block affected; all properties were rented, and costs were not rechargeable. A second RP has completed the cladding replacement works with no recharges to leaseholders. This RP has planned further works to remove all combustible material from the balconies and terraces and is waiting for the outcome of their bid from the Building Safety Fund; the initial bid was rejected and is now going through the appeal process. They have reported that some leaseholders have managed to complete on sales without a full EWS1 certificate.

4.2	In addition, a third RP, with a block held through a lease, has an up-to-date fire FRA and the freeholder is responsible for replacing the cladding. The freehold was sold in September 2020 and received initial funding approval in October 2020. A new funding application was submitted, and a decision is expected by the end of June 2021. The owner of the building has confirmed they plan to replace the cladding with fibre cement panels. Supplementary information submitted to the planning team has been approved. The block is monitored by Building Control and Environment Health.

4.3	Another RP has seven blocks in Barnet over 18 metres that require fire safety work. Funding has been approved for one block and is still waiting for feedback from MHCLG on the remaining blocks. They are still in negotiations with the contractors at each of the sites with two contractors agreeing to undertake the remediation works.

4.4	All large RPs in the borough, including those with buildings over 18 metres, are in regular communication over fire safety of their affordable housing. Information about government funding has been shared with RPs, along with the council’s pledge of support to the “End our Cladding Scandal”.

# 5. Private Sector buildings (residential and commercial)

5.1	Contact has been made with the owners of eight potentially high-risk ACM clad blocks and information notices served. Two private sector blocks have plans to replace the cladding and requested funding from the government to assist with replacement. In both cases, a planning and building control application has been submitted for the proposals with work due to start following approvals. One of these has been inspected with the LGAs Joint Inspection Team (JIT) and an Improvement Notice is likely to be required under the Housing Act 2004. The JIT are to submit their inspection report to the council for review.

5.2	An additional high-rise block, identified and inspected in September 2019, was served with an Improvement Notice by the Fire Authority which has since been complied. It was also inspected by Barnet and the JIT who reported back to the building owners and the Fire Authority. Following liaison with the council and the Fire Authority, extensive work has been and is being completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council is in the process of taking legal action under the Housing Act 2004 to abate Category 1 hazards identified under the Housing Act 2004. The notice is due to be served by the end of July 2021.

5.3	Following wider concerns about the safety of some non-ACM systems, the government requested a further exercise to identify external wall covering on all buildings higher than 18 metres in their area. The review by Building Control Officers was completed and the council has written to landowners/landlords to seek further information to identify the type of insultation used for each building and any external features such as balconies, where required, to update the national dataset. The initial exercise was completed in May 2020 and the outstanding cases are being followed-up. Work continues with the government and Fire Authority to ensure the ongoing safety of residents. Over recent weeks there have been two sites with ACM cladding referred to the council for follow-up, following the service of notices by the Fire Authority. These have been followed up and documentation is now being reviewed to check the safety of onsite systems.

Appendix B: Barnet Council Fire Safety Action Plan (June 2021)

1.1	The table below captures only actions that remain ongoing at the time fire safety was last reported to the Housing & Growth Committee, together with any new actions that have arisen.

Action	Status	Notes
Undertake high priority works identified in surveys	Ongoing	High priority works are practically complete.
Work with government and RPs to ensure actions to address any fire safety concerns are addressed	Ongoing	Two RPs with blocks with ACM panels that failed tests have completed the remedial works or are close to completing. One further ‘leased’ building still requires remedial action.
Liaison with owners of blocks with failed ACM cladding	Ongoing	One block has confirmed that funding was secured for recladding works. They have reported that some leaseholders have managed to complete on sales without a full EWS1 certificate. The second block submitted supplementary information to the Planning team, which has been approved. The block is monitored by Building Control and Environmental Health.
Actions from Fire Risk Assessments for commercial units beneath residential	Ongoing	An extensive review of each commercial premises has been completed, which confirmed suitable arrangements and inspection regimes are in place. Two of 42 properties raised concern and additional enforcement was taken. One surrendered their lease following enforcement and the other complied with the London Fire Brigade inspection and was subsequently considered not to pose further risk. All properties are being monitored as part of the Capita non-managed estate (KPI24c) regime to give ongoing assurance.
Implement the requirements of the Building Safety and Fire Safety Bills	Ongoing	The revised requirements for council and other landowners are being reviewed to ensure measures are in place to deliver full compliance. 21 council buildings are likely to be ‘in-scope’.