Housing & Growth Committee

Fire safety update – February 2022

1.	Summary

1.1	This report provides an update on the progress of fire safety works within the borough since the last update to Housing & Growth Committee in November 2021.

# 2. National updates
2.1	The Building Safety Bill, which takes forward the government’s commitment to reform the building safety system set out in Building a Safer Future, has completed the third reading in the House of Commons and is on the second reading in the House of Lords. This is the first opportunity for members of the Lords to debate the key principles and main purpose of a Bill and to flag up any concerns or specific areas where they think amendments (changes) are needed. After the second reading the Bill will go onto the committee stage where detailed line by line examination and discussion of amendments takes place.

2.2	In January 2022, the government announced a new plan to protect leaseholders from paying to rectify unsafe cladding. This included scrapping the proposal for loans for leaseholders of medium-rise buildings and adding new statutory protections for leaseholders within the Building Safety Bill. Clauses in the Building Safety Bill will allow the government to introduce a levy on developers of high-rise buildings. The next phase of the Building Safety Fund (BSF) will be opened and a new portal will enable leaseholders to check the status of their buildings’ application to this. An amendment to the Building Safety Bill will extend the legal right of building owners and leaseholders to seek compensation from developers for safety defects from up to 15 years old to up to 30 years old.

# 3. Key local updates
# Council Housing
# 3.1 The programme of remedial works planned by the council have been completed for the Category 1 High Priority Works. The Category 2 and 3a Additional Fire Safety Works have been completed at Longford Court, and Norfolk Close and Prospect Ring will be fully completed by the end of March 2022.

3.2	The installation of sprinklers at the Upper Fosters towers has been completed and the Granville Road towers are due to complete in April 2022. The installation of sprinklers to sheltered housing blocks and hostels are mostly being completed alongside other scheduled works.

3.3	Expert consultants have been undertaking in-depth (Type 3 and 4) Fire Risk Assessments (FRAs) at low and medium-rise blocks and any urgent works actioned as a priority. An assessment of future investment need is being developed and provision incorporated within the Housing Revenue Account business plan.

3.4	The High-Pressure Laminate (HPL) cladding systems fitted to the three blocks (Clare, Norden and Whychcote Point) on the Whitefields Estate has been removed and the original fire strategy for the block reinstated.

3.5	On 1 March 2022, the second phase of works will commence on the Holmesdale and Stanhope medium-rise Large Panel System (LPS) blocks.
# Registered Providers
3.6	Currently there are four Registered Providers (RPs) with confirmed ACM or non-ACM (but combustible) cladding on blocks[1].
[1] This can change over time with updated government guidelines and monitoring arrangements.

  1. One RP has completed all works to the block affected.

  1. A second RP has completed the cladding replacement works and has planned further works to remove all combustible material from the balconies and terraces. They are still waiting for the outcome of their bid from the BSF. They have confirmed the block is safe to occupy following measures put in place converting the building to an evacuation rather than a stay put policy.

  1. A third RP, with a block held through a lease, has an up-to-date FRA and the freeholder is responsible for replacing the cladding. They have been awarded funding from the GLA and the freeholder has appointed a contractor with a view to starting works in February 2022.

  1. A fourth RP has several blocks located in four different estates in Barnet that require fire safety work. Works are either progressing or the scope is being negotiated with developers. BSF bids have been submitted where eligible.

Private Sector Buildings

3.11	Contact has been made with the owners/agents of 34 potentially high-risk and medium risk ACM clad blocks. Two private sector blocks have plans to replace the cladding and funding has been approved by government to assist with replacement. In both cases, a planning and building control application has been submitted for the proposals.

3.12	Inspections have been completed on three buildings due to the high-risk of the structures. Two of these have been inspected with the LGA’s Joint Inspection Team (JIT). One of these was identified and inspected in September 2019 and was served with an Improvement Notice by the Fire Authority which has since been complied with. Following liaison with the council and Fire Authority, extensive work continues to be completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council served Improvement Notices under the Housing Act 2004 to abate Category 1 hazards identified and all of these have been appealed.

3.13	Full details of the local context are set out in Appendix A, with progress against the defined action plan set out in Appendix B.

APPENDIX A: Fire safety and the council’s response to the Grenfell Tower tragedy (February 2022)
# 1. Introduction

1.1	This report provides a progress update on fire safety issues in Barnet, including progress on the agreed package of fire safety improvement works for council properties managed by Barnet Homes, as well as activity in relation to relevant Registered Providers (RPs) and Private Sector housing stock.
# 2. Building a Safer Future (Fire Safety Bill and Building Safety Bill)

2.1	Building a Safer Future (BSF) is a government-led initiative in response to the Grenfell Tower tragedy. It is a framework within which the shortcomings identified in the post-Grenfell review of Building Regulation and Fire Safety can be addressed. These shortcomings include the way high-rise residential buildings are built and managed. BSF is also intended to deal with situations where residents may raise concerns about the safety of their buildings, which they may feel are not taken seriously by their landlord. Two key pieces of legislation support this initiative: the Fire Safety Act and Building Safety Bill.

2.2	The Building Safety Bill, which takes forward the government’s commitment to reform the building safety system set out in Building a Safer Future, has completed the third reading in the House of Commons and is on the second reading in the House of Lords. This is the first opportunity for members of the Lords to debate the key principles and main purpose of a Bill and to flag up any concerns or specific areas where they think amendments (changes) are needed. After the second reading the Bill will go onto the committee stage where detailed line by line examination and discussion of amendments takes place.

2.3	The changing legislative framework for fire safety will introduce additional requirements for building safety and the management of our buildings and wider housing stock within the borough. These requirements are being identified through an officer working group and an action plan is being progressed.

# 3. Council Housing

3.1	The fire safety delivery programme for council housing stock continues to progress well:

Item	Cost	Status
Granville Road cladding removal, recladding and associated costs	£5,922,900	Completed
Category 1 High Priority works	£9,220,433	Completed
Additional fire safety works to high rise buildings (Category 2 and 3a works)	£12,656,667	In progress
Installation of sprinklers to High Rise blocks with 2 stairwells	£3,220,000	In progress
Installation of sprinklers to sheltered housing blocks	£2,330,000	In progress
Installation of sprinklers to hostels	£150,000	In progress
Works to low and medium rise blocks (Inc. undertaking of type 3 FRA’s and any urgent arising works	£7,900,000	In progress
Replacement of composite fire doors	£10,500,000	In progress
Total	£51,900,000

3.2	Granville Road Recladding - Completed.

3.3	Category 1 High Priority Works – Completed. The works to flats and communal areas of high-rise blocks (Whitefields, Grahame Park and Silk House & Shoelands) have been completed. This included works to improve the front doors to flats and fire alarm warning systems.

3.4	Additional fire safety works (Category 2 and 3a) - The works at Longford Court have been completed. Norfolk Close and Prospect Ring will be fully completed by the end of March 2022. The completion has been impacted by difficulties accessing a small number of properties. Works carried out by Wates will conclude in February 2022 with additional ventilation works being undertaken in Spring 2022.

3.5	Installation of sprinklers to blocks of flats with 10 or more floors and 2 or more stairwells – Fire safety works at Granville Road towers commenced in July 2021 following a re-tendering exercise. These works are progressing well and due to complete in April 2022. The works at the Upper Fosters towers have been completed.

3.6	Installation of sprinklers to sheltered housing blocks and hostels - Most works were scheduled for 2022/23 and 2023/24; however, consideration was given to accelerating the installation at certain schemes where other disruptive works are scheduled as part of the wider capital investment programme. This has been agreed and works are being undertaken at all hostels and sheltered blocks, other than the Potteries and Hanshawe Drive which will follow in Spring 2022. These works are on target to meet these timescales.

3.7	Fire safety works at St John’s Close sheltered housing block have commenced and will be completed in 2022 following significant Covid-19 delays. These are being incorporated into other works that include a new heating system and electrical upgrades.

3.8	Works to low and medium rise blocks (incl. Type 3 Fire Risk Assessments (FRAs) and any urgent arising works) - Expert consultants have been undertaking in-depth (Type 3 & 4) FRAs and any urgent works actioned as a priority to all blocks, with other observations forming part of a longer-term planned programme of improvements. The survey programme has been largely completed, and an assessment of future investment need is being developed and provision incorporated within the Housing Revenue Account business plan.

3.9	Replacement of composite fire doors – The programme of fire door replacements has continued with c.3200 door installations now completed, with c.570 doors remaining for replacement. An agreement has been reached with the contractor for faulty doors to be replaced at the contractor’s expense and liability resolved through independent adjudication when the work is finished. Another 1400 doors are being replaced through separate arrangements, most of which form part of existing fire safety works in programme.

3.10	Whitefields Estate - tower block cladding system – The High-Pressure Laminate (HPL) cladding systems fitted to the three blocks (Clare, Norden and Whychcote Point) on the estate has been removed and the original fire strategy for the block reinstated.

3.11	Large Panel System (LPS) buildings - An expert consultant’s report on Holmesdale and Stanhope medium-rise LPS blocks in N11 has determined that risk mitigation measures are necessary here and this work is progressing well, with the second phase of works due to commence on 1 March 2022 following a tender exercise. Fire safety surveys at the blocks have highlighted the need to install additional measures in the top floor flats and a range of options are being offered to tenants and leaseholders to ensure risk mitigation measures are safely implemented.

3.12	Responding to changing legislation - Barnet Homes has completed an initial assessment of how the new requirements of the Building Safety Bill and Fire Safety Act will impact on the council housing stock in Barnet and have confirmed that 16 buildings will be considered ‘in-scope’ of the Building Safety Bill within the council stock. Associated resources have been identified and a provision made within the current version of the Housing Revenue Account Business Plan. Further clarity regarding how the duties of the specific duty holder roles outlined in the Bill will be discharged will be forthcoming once the Bill itself has received Royal Assent.

# 4. Registered Providers (RPs)

4.1	Currently there are four RPs with confirmed ACM or non-ACM (but combustible) cladding on blocks[2].
[2] This can change over time with updated government guidelines and monitoring arrangements.

4.2	One RP has completed all works to the one block affected. All the properties were rented, and costs were not rechargeable.

4.3	A second RP has completed the cladding replacement works with no recharges to leaseholders. This RP has planned further works to remove all combustible material from the balconies and terraces and is still waiting for the outcome of their bid from the Building Safety Fund; the initial bid was rejected and is now going through the appeal process. They have reported that some leaseholders have managed to complete on sales without a full EWS1 certificate.  They have instructed solicitors to take further action on resolving all outstanding matters on the building, which will include a review to identify the overall risks and to suggest practical remediation options. They are assessing the new PAS9980 (code of practice for the fire risk appraisal of external wall construction and cladding of existing multistorey and multi-occupied residential buildings) document and how this can be applied to buildings. They have confirmed the block is safe to occupy following measures put in place converting the building to an evacuation rather than a stay put policy.

4.4	A third RP, with a block held through a lease, has an up-to-date FRA and the freeholder is responsible for replacing the cladding. The freehold was sold in September 2020 and received initial funding approval in October 2020. A new funding application was submitted and the GLA awarded the funding. The freeholder has appointed a contractor and is planning to start works before the end of February 2022. The block is being monitored by Building Control and Environment Health (further details can be seen in Section 5).

4.5	A fourth RP has several blocks located in four different estates in Barnet that require fire safety work:

- Estate 1 - the developer should complete all works to the cavity barrier to the external wall system by the end of February 2022.  The BSF application will be revised to reflect the removal of the insulation.  The BSF bid has passed the first two stages of the review.  Residents are updated via regular residents' meetings.
- Estate 2 - negotiations with the developer are still progressing to remediate all the blocks.  They have agreed the developer will carry out works and are finalising the scope of this and the costs.  There is only one block in this estate that is eligible for BSF funding and the RP is waiting for the outcome of the application.  Residents are regularly communicated with via residents’ meetings.
- Estate 3 - the developer has started works on two blocks to remediate the cavity barriers and should complete by March 2022.  They have agreed to remediate two further blocks and should decide exact details by the end of February 2022.  For another block in this estate, works are being undertaken to replace the ACM and wooden balconies, with completion due by June 2022.
- Estate 4 - the RP is still in negotiation to agree the scope of works and responsibility and are also waiting for the outcome to the BSF application.  Regular residents’ meetings are taking place with these blocks to keep residents updated on progress.

4.6	All large RPs in the borough remain in regular communication over the fire safety of their affordable housing.

# 5. Private Sector buildings (residential)

5.1	Contact has been made with the owners/agents of 34 potentially high-risk and medium risk ACM clad blocks. The majority of these are managed by the same agent who the council meets regularly. Two private sector blocks have plans to replace the cladding and funding has been approved by government to assist with replacement. In both cases, a planning and building control application has been submitted for the proposals with work due to start following approvals.

5.2	Inspections have been completed on three buildings due to the high-risk of the structures. Two of these have been inspected with the LGA’s Joint Inspection Team (JIT). One of these was identified and inspected in September 2019 and was served with an Improvement Notice by the Fire Authority which has since been complied with. Following liaison with the council and Fire Authority, extensive work continues to be completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council served Improvement Notices under the Housing Act 2004 to abate Category 1 hazards identified and all of these have been appealed, in the first instance to First Tier Tribunal, but the appellants have requested that the case goes straight to the Upper Tribunal due to the nature of some of the appeal grounds. The council is awaiting directions from tribunal, but this will be an expensive and time-consuming process.

5.3	Enforcement action against such blocks is difficult and very time consuming, involving detailed inspection and the obtaining, review and analysis of a significant number of complex documents, in order to ascertain the safety and completeness of systems and structures in place. Often block owners either don’t have the relevant paperwork or it isn’t sufficient. Service of statutory notices on such blocks can involve issuing hundreds of notices on multiples of different leaseholders, freeholders and relevant parties incurring a significant cost.

5.4	A part-time dedicated resource has been temporarily recruited to concentrate on improvement of high-risk blocks whilst a full-time permanent officer is recruited. This has enabled a robust infrastructure to be set up for this project.

Appendix B: Barnet Council Fire Safety Action Plan (February 2022)

1.1	The table below captures only actions that remain ongoing at the time fire safety was last reported to the Housing & Growth Committee, together with any new actions that have arisen.

Action	Status	Notes
Undertake high priority works identified in surveys	Completed	High priority works have been completed.
Work with government and RPs to ensure actions to address any fire safety concerns are addressed	Ongoing	One RP has completed all works to the one block affected. / A second RP has completed the cladding replacement works and has planned further works to remove all combustible material from the balconies and terraces. They are still waiting for the outcome of their bid from the BSF. They have confirmed the block is safe to occupy following measures put in place converting the building to an evacuation rather than a stay put policy. / A third RP, with a block held through a lease, has an up-to-date FRA and the freeholder is responsible for replacing the cladding. Funding has been awarded from the GLA and the freeholder has appointed a contractor with a view to starting works in February 2022. / A fourth RP has several blocks in four different estates that require fire safety work. Works are either progressing or the scope is being negotiated with developers. BSF bids have been submitted where eligible.
Liaison with owners of blocks with failed ACM cladding	Ongoing	Contact has been made with the owners/agents of 34 potentially high-risk and medium-risk ACM clad blocks. Two private sector blocks have plans to replace the cladding and funding has been approved by government. In both cases, a planning and building control application has been submitted for the proposals. / Inspections have been completed on three buildings due to the high-risk of the structures. Two of these have been inspected with the LGA’s Joint Inspection Team (JIT). One of these inspected in September 2019 and served with an Improvement Notice by the Fire Authority which has since been complied with. Following liaison with the council and Fire Authority, extensive work continues to be completed to the block and cladding removal is ongoing. A revised FRA has been undertaken. The council served Improvement Notices under the Housing Act 2004 to abate Category 1 hazards identified and all of these have been appealed, in the first instance to First Tier Tribunal, but the appellants have requested that the case goes straight to the Upper Tribunal due to the nature of some of the appeal grounds. The council is awaiting directions from tribunal.
Actions from Fire Risk Assessments for commercial units beneath residential	Ongoing	An extensive review of each commercial premises was completed, which confirmed suitable arrangements and inspection regimes are in place. All properties continue to be monitored as part of the Capita non-managed estate (KPI24c) regime to give ongoing assurance. / There was a low level of response from the commercial units for updated information in November. A follow up request was sent out in December and remaining returns were received in January 2022.
Implement the requirements of the Building Safety and Fire Safety Bills	Ongoing	Barnet Homes has completed an initial assessment of how the new requirements of the Building Safety Bill and Fire Safety Act will impact on the council housing stock in Barnet and have confirmed that 16 buildings will be considered ‘in-scope’ of the Building Safety Bill within the council stock. Associated resources have been identified and a provision made within the current version of the Housing Revenue Account Business Plan.