# CHIPPING BARNET AREA COMMITTEE

Community Infrastructure Levy (CIL) - Budget & Scheme Update
9th March 2022
25

Commentary
The total available budget is £155,225
Note: The Tudor Park pavilion project has been allocated £100k from the 2022/23 budget (not accounted in these figures).
The under/overspends figure is being finalised as the Re: Highways invoicing is finalised. The net impact is not expected to be material, and the current impact is a net underspend of £45,026.
No future overspends should be committed without either prior approval of the Area Committee Chair or the Area Committee.
26

27

CHIPPING BARNET AREA COMMITTEE - OPEN CIL SCHEME UPDATES (non-highways)

Ward	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Overspend to approve / £	Delivery Service	Commentary	Expected Delivery / Date
Coppetts	2021122	1811012021	Allotmentz Kitchen Unit - Mobile_ Kitchen, funding for the refurbishment of the vehicle	Barry Rawlings	2,000		Community Grant	The work on the taxi has been started and expected to be completed in May-22	May-22
Coppetts	2021122	1811012021	Peace Statue in Friary Park - restoration and replacement of dove & septre (match funding)	Reema Patel	20,526		Barnet - Estates	Statue is due to be moved to workshop mid-Mar with reinstatement expected Jun-22	Jun-22
High Barnet	2021122	1811012021	Hadley Green path installation between Christ Church Lane & Hadley Green West, and Hadley Green West to path behind Windmill House (request / of Hadley Residents Association)	David Longstaff	20,000		Barnet - Greenspaces	Feb 22: Works to be programmed for Spring when the ground conditions allow for this type of works to be completed.	Q2 22/23
High Barnet	2021122	1811012021	Hadley Green litter bins_- provision of 20 new modern covered litter bins	Wendy Prentice	10,000		Barnet - Greenspaces	Feb 22: Order for bins raised and installation will be arranged once delivery has been confirmed.	Q4 21/22
East Barnet	2021122	1811012021	Outdoor gym equipment for Victoria Recreation Ground	Felix Byers	35,000		Barnet - Greenspaces	Feb 22: Our equipment supplier has released a new improved style of equipment as such as agreed with Councillor Byers, we will be looking to enhance the concept design utilising additional other funding in order to deliver an improved gym installation. We have received the designs and are working to confirm these prior / to raising an order.	Jun-22
Coppetts	2021/22	29/06/202l	Halliwick- park furniture (picnic tables) and parks games equipment (variety of park installed games)	Pauline Coakley­ Webb	13,680		Barnet - Greenspaces	Feb 22: This project has been merged with the other Halliwick project. Table Tennis Tables have been ordered and will be programmed for installation once the ground conditions allow, the picnic tables have been ordered and awaiting delivery. The goals remain on hold until the location for installation can be agreed.	Q1 22/23
Totteridge	2021/22	29/06/2021	Enhance & protect WW2 Air Raid Warden's post on the green space adjacent to Brook Farm (heritage / request) - Public Realm	Alison Cornelius	3,000		Barnet - Greenspaces	Feb 22: All works agreed and ordered. The plaque has been delivered and the door/gate is being fabricated and once complete will be installed.	Q4 21/22
High Barnet	2021/22	29/06/2021	Refurbishment of Tudor Park Pavilion, and establishment of a cafe	David Longstaff	100,000		Barnet - Greenspaces	The structural survey confirms substantial structural defects and options and costs for remediation will be prepared by a Quantity Surveyor. The heritage funding bid was unsuccessful. / Budget of £200k has been allocated (£100k from 21/22 and £100k from 22/23 / by the AC)	Aug-22

28

CHIPPING BARNET AREA COMMITTEE - OPEN CIL SCHEME UPDATES (non-highways)

Ward	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Overspend to approve / £	Delivery Service	Commentary	Expected Delivery / Date
East Barnet	2020/21	20/01/2021	Provision of Play Equipment in the North of Oakhill Park	Lawrie Williams	25,000		Barnet - Greenspaces	Jan 22: Designs have come through. Cllr is submitting an amended bid for an / additional £50k CIL funding. Feb: No further update	Q1 22/23
Coppetts	2020/21	20/01/2021	Halliwick Recreation Ground - Table Tennis Table	Pauline Coakley­ Webb	8,000		Barnet - Greenspaces	Jan 22: Orders have been raised. Issues with waterlog conditions, works suspended until summer. / Feb 22: This project has been merged with the other Halliwick project.	Q1 22/23
Coppetts	2020/21	20/01/2021	Hollickwood Park- Park Improvements	Pauline Coakley­ Webb	16,900		Barnet - Greenspaces	Feb 22: Orders raised for basketball court works just awaiting a commencement date. Quotation for the signage works has been received and the order raised.	Q1 22/23
Totteridge	2019/20	03/10/2019	Swan Lane Open Space- Installation of older children's play equipment	Alison Cornelius	25,000		Barnet - Greenspaces	Jan 22: Work on hold until Spring when weather conditions improve. Equipment in storage. / Feb 22: No further updated as works paused until ground conditions allow for safe construction.	Q2 22/23
Various	2017/18	19/02/2018	The Mayor of Barnet's Golden Kilometre Marked Routes - 10 Parks	Caroline Stock	25,000		Barnet - Greenspaces	Feb 22: Quotations being arranged for an Active Trail as part of this scheme for Victoria Recreation Ground, Riverside Walk and Old Courthouse Recreation Ground. We anticipate a return of some of the allocated funding, we will be able / to confirm once the quotes have been received.	Q2 22/23

29
Ward	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Highways Project	Commentary	Expected Delivery Date
Brunswick Park	2018/19	04/10/2018	Parking Brunswick Park Road	Julian Teare	1,500	BC/001540-04- 02	Works commenced on 24 Jan, expected completion mid Feb	Q4 21/22
Brunswick Park	2019/20	03/10/2019	Parking - Church Hill Road (Footway Parking)	Julian Teare	3,500	BC/001750-05	2 applications received from residents for dropped kerbs. Implementation package to be issued to contractor to programme works. Implementation to be aligned with dropped kerbs. One dropped kerb application awaiting outcome to grant application, / decision expected mid Feb	Q4 21/22
Brunswick Park	2020/21	01/01/2021	Hampden Way Bollards	Roberto Weeden-Sanz	5,000	BC/001966-11	Scheme completed on 24 January	Complete
Coppetts	2016/17	06/07/2016	Parking - Newton Avenue/Pembroke Road	Pauline Coakley-Webb	2,000	BC/001022-02	Aligned with NlO Waiting restrictions scheme. Implementation / package issued to contractor to programme works. Estimated completion Q4 subject to contractor.	Q4 21/22
Coppetts	2020/21	06/10/2020	NlO Waiting Restrictions	Committee Report	5,000	BC/001966-06	Aligned with Newton Avenue/Pembroke Road scheme. Implementation package issued to contractor to programme works. / Estimated completion Q4 subject to contractor. *	Q4 21/22
East Barnet	2017/18	08/03/2018	Parking Survey JCOSS Implementation	Committee Report	8,000	BC/001409-10	90% complete. Site meeting took place with Cllr Williams to review layout of DYLs and request to be raised by Ward Cllr for a consultation to take place to change original design. Outcome will instruct whether remaining works to be completed. Highways / officers to raise this with Ward Cllr at ward walk.	On hold
Coppetts	2021/22	21/04/2021	RyalI Court and Oakleigh Road North WR	Barry Rawlings	2,000	BC/002031-03	Implementation package issued to contractor to programme works. Estimated completion Q4 subject to contractor	Q4 21/22

30
Ward	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Highways Project	Commentary	Expected Delivery Date
Oakleigh	2021/22	30/06/2021	Oakleigh Park South VAS	Committee Report	26,400	BC/002064-07	Implementation package to be issued to contractor. Road markings to be complete mid-February (weather dependent). Delivery of VAS expected by end of March and Implementation now expected early / April.	Q1 22/23
Totteridge	2020/21	20/01/2021	Northcliffe Drive	Alison Cornelius	3,000	BC/001966-10	Scheme complete	Complete
Totteridge	2021/22	21/04/2021	Benches Totteridge Station and Dollis Brook x2	Richard Cornelius	3,500	BC/002031-06	Specification now agreed with Cllrs. Quotation received, and implementation package to be prepared issued to the contractor	Q1 22/23
Totteridge	2021/22	21/04/2021	Totteridge Village/ Lane and Pine Grove N20 WR	Alison Cornelius	2,000	BC/002031-05	Scheme complete	Complete
Underhill	2021/22	30/06/2021	Barnet Hospital - CPZ Review/ Implementation incl. Bells Hill (experimental)	Committee Report	30,000	BC/002064-09	Meeting took place with resident to address concerns raised, and it was agreed with LBB Parking Team to proceed with as is. / Implementation package issued to contractor to programme works. / Estimated completion Q4 subject to contractor.	Q4 21/22

# CHIPPING BARNET AREA COMMITTEE

Road Safety & Parking - Budget & Scheme Update
9th March 2022
31

32

Commentary
Additional funding of £200,000 was approved at the Policy & Resources Committee on 9th December

33
Area	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Highways Project	Commentary	Expected / Delivery Date
Chipping Barnet	2021/22	N/A	Longmore Avenue	Committee Report	33,100	BC/002064-10	Consultation to commence on 10 March. Estimated completion June 22.	Jun-22
Chipping Barnet	2021/22	Jun-21	Barnet Hospital CPZ	Committee Report	34,890	BC/002064-09	Meeting took place with resident to address concerns raised, and it was agreed with LBB Parking Team to proceed with as is. / Implementation package issued to contractor to programme works. Estimated completion Q4 subject to contractor.	Mar-22
Chipping Barnet	2021/22	Jun-21	Barnet Road	Committee Report	15,000	BC/002064-03	Implementation originally scheduled for mid-January, but electrical supplier has raised issue during implementation. Alternative locations to be reviewed before scheme progresses.	Mar-22
Chipping Barnet	2021/22	Jun-21	Gallants Farm - VAS & Slow Marking	Committee Report	17,820	BC/002064-06	Design in progress, smiley face VAS has been requested for this location. Implementation package to be completed by end of Feb. Estimated completion April 22	Apr-22
Chipping Barnet	2021/22	Jun-21	Hadley, Clifford and Woodford Roads	Committee Report	19,800	BC/002064-08	COD to be submitted for approval in February. Implementation package to be produced and issued to contractor to programme works.	Mar-22
Chipping Barnet	2021/22	Jun-21	Hendon Wood Lane	Committee Report	12,870	BC/002064-04	Detail design completed. Implementation package to be prepared for issue to contractor. Estimated completion April 22.	Apr-22
Chipping Barnet	2021/22	Jun-21	Parkside Gardens	Committee Report	48,950	BC/002064-05	COD being finalised for submission in Feb. Topographical survey now completed and detailed design now in progress for completion late / March Estimated completion Jun-22.	Jun-22
Chipping Barnet	2021/22	N/A	York Way, N20	Members Request	5,000	TBC	Surveys to commence 21 Feb	Mar-22
Chipping Barnet	2021/22	N/A	Manor Drive/1-10 Raleigh Drive, Whetstone N20	Members Request	7,000	TBC	Surveys to commence 21 Feb	Mar-22

34
Area	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Highways Project	Commentary	Expected Delivery Date
Hendon	2021/22	N/A	Aerodrome Road	Committee Report	35,630	BC/002063-10	Consultation Feb 22, design March/April and Implementation May/June22	Jun-22
Hendon	2021/22	N/A	Allington Road/ Sevington, Vivian Avenue/Elliot Road - OD Survey	Councillor Don	9,500	BC/002063-07	Programmed dates to be finalised by end of January	TBC
Hendon	2021/22	N/A	Dallas Road NW4 - Speed Survey	Councillor Don	2,000	BC/002063-06	Engagement with Cllrs to agree locations Speed survey to take place in February. Estimated completion March 22.	Mar-22
Hendon	2021/22	N/A	Edgwarebury Lane	Committee Report	34,870	BC/002063-11	Consultation Feb 22, design March/April and Implementation May/June22	Jun-22
Hendon	2021/22	N/A	Frith Lane opposite Finchley Golf Club / - Feasibility Study	Residents Forum	5,000	BC/002063-09	Feasibility due to commence. Estimated completion April subject to TfL engagement	Apr-22
Hendon	2021/22	N/A	The Millway	Councillor Richman	£12,400	TBC	Funding allocated. Scheme to be programmed	TBC
Hendon	2021/22	N/A	Saracens School	Councillor Narenthira	8,000	TBC	Funding allocated. Scheme to be programmed	TBC
Hendon	2021/22	N/A	Cool Oak Lane	Councillor Duschinsky		TBC	Funding allocated. Scheme to be programmed	TBC
Hendon	2021/22	N/A	Rushgrove Avenue	Councillor Narenthira	5,000	TBC	Funding allocated. Scheme to be programmed	TBC

35

Area	Financial Year	Committee Date	Scheme Description	Ward Member	Budget Allocation / £	Highways Project	Commentary	Expected Delivery Date
Finchley & / Golders Green	2021122	Nov-21	Long Lane	Committee Report	8,250	BC/002065-07	Consultation planned to commence in Feb 22, followed by the design in April and estimated completion Q2	Jun-22
Finchley & / Golders Green	2021122	Nov-21	Tillingbourne Gardens	Committee Report	18,700	BC/002065-09	Consultation planned to commence in Feb 22, followed by the design in April and estimated completion Q2	Jun-22
Finchley & / Golders Green	2021122	Nov-21	Woodgrange Ave	Committee Report	1,375	BC/002065-08	Consultation planned to commence in Feb 22, followed by the design in April and estimated completion Q2	Jun-22
Finchley & / Golders Green	2021122	Jun-21	Hampstead Way/ Meadway	Committee Report	30,000	BC/002065-03	Consultation completed. Implementation package to be produced and issued to contractor to programme works. Estimated completion Q1	Mar-22
Finchley & / Golders Green	2021122	Jun-21	Cranbourne Gardens & / Leeside Crescent	Committee Report	13,200	BC/002065-04	Design to be completed by February. Estimated completion Q2	Mar-22
Finchley & / Golders Green	2021122	N/A	Fallowfields Estate, N12 / Fallowfields Drive	Councillor Hutton	5,000	BC/002065-06	Design in progress, consultation currently planned to commence 10 February. Estimated completion early Q2	Jun-22

36
Area	Ward Cllr	Location	Request	Response	Stage
Hendon	sd Cllrschinsky	Woodcroft Ave and Bunns Lane	The need for the introduction of a crossing point around Woodcroft Avenue towards Bunns Lane NW7 and full junction review will have to be carried out in conjunction with the j/w Lyndhurst and j/w Graham Park Way where 2 mini roundabouts are present at the moment, and it will also require involvement with London Buses in their turning movements and route.	Highways officers reviewing costs for this Feasibility Study.	Technical Assessment / - Highways
Hendon	Cllr Duschinsky	Copthall School	Proposed double yellow lines along upper Page Street and some section with loading restriction Temporary suspended permit holder bays to observe if congestion and traffic problem improves Consider permanently suspended permit holder bays subject to consultation / Speed survey to be carried out to determine speed and possibly install VAS signs Feasibility of 20mph speed limit with option to install speed cushions / Feasibility to install enforcement camera subject to the agreement of parking enforcement team	Currently being reviewed by Officers	Technical Assessment - Highways
Hendon	Councillor Wardle	Hartland Drive	Installation of double yellow lines on the junction of Hartland Drive and Edgwarebury Lane.	Taken forward with 5106 funding	Other Funding
Hendon	Councillor Conway	The Greenway	Review of Parking Bays	Currently under investigation with Highways Officers	Technical Assessment - Highways
Hendon	Councillor Conway	Deansbrook Road	Deansbrook Road zebra crossing review for additional measures	Site meeting to be arranged with Councillor	Technical Assessment / - Highways
Hendon	Councillor Conway	The Greenway	Review of Parking Bays	Currently under investigation with Highways Officers	Technical Assessment - Highways

37
Area	Ward Cllr	Location	Request	Response	Stage
Hendon	Councillor Don	Rookery Way	Request for Pedestrian Crossing- Rookery Way junction of The Hyde, Highbury Road, and Rookery way NW9	note this item will be addressed as part of wider scheme developments. / This is still in the draft LIP programme we have sent to Tfl just recently to seek funding for the design to progress next FY. But it is a significant signals scheme which would be timely and at a high cost / It also has links to the AS parallel cycle route scheme we are in the process of designing and both schemes need to be considered together. So, it has not been 'de-prioritised', and is still something we are pursuing- but it is subject to / availability of funding from Tfl.	Other Funding
Hendon	Cllr Narenthira	Varley Parade	Due to the bollards by the traffic lights on the AS by Varley parade and the presence of so many parked cars, vans and motorbikes, there is no access for pedestrians to walk from the row of shops to reach the pedestrian traffic lights crossing point safely, The dropped kerb area outside the pub to allow access for wheelchairs and push chairs to the signalised crossing on the AS is simply ignored with cars parking and blocking the pedestrian access route all along this frontage area	Site observation and issue noted Recommendation: / To resolve the concerns raised, an engineer visited site with ward Cllr and recommends creating a pedestrian area between the parked vehicles which will lead to the signalised crossing, separated with the installation of approximately 4- bollards which would prevent vehicles from parking in this area and give access to wheelchairs and buggies. / There is also a possibility of formalising the parking arrangement by introducing marked bays with "30min free parking and no return within 1 hour" restriction opposite the shops to prevent double parking, which currently restricts pedestrians' visibility at the crossing point across Varley Parade.	Final Approval
Hendon	Cllr Narenthira	Sheaves hill Avenue	Speeding between AS and Colindeep lane stretch of Sheaveshill Avenue. / This street is used by many parents and kids who attend Colindale School. Cars are parked on both sides. There is a blind bend on this street near Courtway which reduces visibility for cars approaching the bend from both directions.	Currently being reviewed by Officers	Technical Assessment - Highways

38
Area	Ward Cllr	Location	Request	Response	Highways Technical / Assessment	LBB Officer Review	Final Approval
Finchley & / Golders Green	Cllr Clarke	Cricklewood Lane	Feasibility study to address concerns raised during Officers & Ward Member site visit including; / Traffic speed - Cricklewood Lane between A41 to Finchley Road, in particular close to the shopping area and All Saints School / Possible build out incorporating sustainable drainage solutions / / planting which would contribute to lowering traffic speed Improvement to public realm	During the site visit various options were discussed including the requirement of a feasibility study to determine the most suitable solution for this location. To also include a speed survey. £7,500 which will include the section between A41 to Finchley Road. Additional £200k of Road Safety funding agreed at P&R in December.	Complete	Complete	Final allocation
Finchley & / Golders Green	Cllr Marshall	Kingsley Way	This location has been raised a number of times through F&GG Resident Forum and to Ward Members. There was also an accident at this location more recently. / To request that Engineers undertake a Feasibility Study to investigate the possible location for the uncontrolled crossing point (dropped kerbs and tactile paving) near the entrance to both parks along with 'SLOW' road markings, also carry out a speed survey to identify the traffic speeds on the approaches to the park entrances, so they can understand if speeding is an / issue on this road.	Following conversations with Engineers and Jackie Staples, it is suggested that a study may be undertaken to review the concerns raised at this location. The cost for a Feasibility Study would be £5,000. Additional £200k of Road Safety funding agreed at P&R in December.	Complete	Complete	Final allocation
Finchley & / Golders Green	Cllr Mittra	Fairlawn Ave	Officers met with Ward Members onsite having received concerns from residents, during the visit it was identified that there were possible solutions that would require a wider feasibility study. The study will be used for Engineers to provide an update to Ward Members/ Committee on their thought around how this location can be improved. The feasibility cost should be raised for £15,000 to review the / points below including other options as identified by Engineers	During the site visit it Officers noted that a feasibility study was required to find a suitable solution. Additional £200k of Road Safety funding agreed at P&R in December.	Complete	Complete	Final allocation

39
Area	Ward Cllr	Location	Request	Response	Stage
Chipping / Barnet	Residents Forum	Potters and Plantagenet Road	Various Safety concerns raised at Residents Forum	It was agreed to consultation for YLs has taken place as part a separate funding. Objections received and officers are currently preparing the response and COD to be drafted for submission beg Feb. Estimated completion expected mid Ql. Paul Sears has been contacted with regards to lighting.	Technical Assessment - Highways
Chipping / Barnet	Councillor rutter	Brunswick Park road (junction with the cemetery)	Request for traffic lights at the mini roundabout Junction with Cemetery	Site visit to be undertaken with Highways officers	Technical Assessment - Highways
Chipping / Barnet	Councillor Weeden- Sanz	Hampden Way	Request for Hedges to be planted on Hampden Way	Site visit to be undertaken with Highways officers	Technical Assessment- Highways
Chipping / Barnet	Councillor Smith	Longmore Ave	Speeding issues on Longmore Ave	Speed survey required. Highways officers reviewing costs	Technical Assessment- Highways